## Slide 1: Introduction to using the Electronic Design Notebook for Capstone Design
Mark Anderson
Aren Paster
The Design Lab at Rensselaer
Rensselaer Polytechnic Institute
Based on a presentation given by
Junichi Kanai and Mark Anderson at the
ASEE St. Lawrence Section 2012 Conference March 24, 2012
Notes: Revised 10/26/2022

## Slide 2: Outline
What is the Electronic Design Notebook (EDN)?
Terminology and Definitions
Implementation – EDN in The Design Lab
Best Practices
Conclusions

## Slide 3: What is the Electronic Design Notebook?
A project management, documentation, and bug-tracking tool
Includes a calendar and Gantt chart to aid visual representation of projects and their deadlines
Supports multiple projects
Provides integrated project management features, issue tracking, and support for multiple version control options
Web-based
Free and open source
Similar to tools used in industry
Adapted from http://en.wikipedia.org/wiki/Redmine, accessed 3/14/2012
Notes: It was influenced by Trac, a software management / bug tracking tool.
The terminology is slightly software oriented but still applies to the various engineering disciplines

## Slide 4: Why Capstone uses EDN
Engineering Functions
Record Keeping
Technical Discussions
Revision Control
Project / Task Management
IT Related
Available Technical Support
Backups
Secure
Academic Related
Visibility of Student Work
User Statistics
EDN Usage Supports Our Capstone Approach
Notes: Open Source Software

## Slide 5: RPI Design Lab site
If it doesn’t say
“The Design Lab at Rensselaer”
then you are NOT ON OUR SITE!
Go to https://designlab.eng.rpi.edu

## Slide 6: Sample Capstone Project Home Page

## Slide 7: List of Electronic Design Notebook features
Overview – summary of issues, users and latest news
Activity – shows recent posts, changes made throughout the project (can specify based on what the user is looking to search for)
Roadmap – dynamically generated display of issues and their related “versions”
Issues – task tracking
Gantt – dynamically generated Gantt chart schedule based on issues and versions that have been created
Calendar – provides a view of the issues in a typical calendar mode
News – posting for general announcement (more pertinent for large groups)
Wiki – to collect shared knowledge, facts, data, etc…
Forums – for discussion of topics
Repository – for shared files with version control (a web display of the data that is integrated with an SVN client installed on users’ computers)
Booty Bay – shared resource management (i.e. loaning equipment, books)
Settings – allows user to adjust system settings for this particular project
Notes: Redmine was initially developed to address software related projects and some of it’s terminology comes from that background.

## Slide 8: User Roles
Roles and Associated Project Members
Can Be Seen on the Overview Page
These are Roles
Each Role may have different privileges

## Slide 9: Terminology
Standard Project Management Term | EDN Equivalent Term
Milestone | Version
Task | Issue
Electronic Design Notebook Terms
Tracker – used to filter Issues when displaying the Issues as a list or a Gantt chart
  This is the “type” of issue.
  Separates day to day “To-Do” items from “Gantt Chart” items
Category – used to filter Issues when displaying the Issues as a list or a Gantt chart
  Can be used to group Issues
  Can be used to separate the subsystems in your project

## Slide 10: Project Management
Identify project tasks and create them as “Issues”
  Assign task owner (“Assignee”) and due date
  Not every task has to start today!
  All tasks don’t end at the same time
On a regular basis, USE the “Issues” list to manage team activities
For multi-semester projects, review any open issues and re-plan them as needed. Do not simply close them!

## Slide 11: Project Management
Effective use of Trackers – Used Across All Projects
  To-Do – used for action items, various task assignments, things to be done
  Features – once a baseline of functionality has been defined, NEW features or functions can be tagged with this Tracker
  Bugs – these are used for any artifact that has been created but has errors. This includes software, fabricated parts, CAD models / drawings, documentation, etc.
Effective use of Categories – Unique to Your Project
  Define categories that match your team’s Work Breakdown Structure (WBS) or Subsystems
      Examples – Software, Hardware, Documentation, Maintenance, Project Management, Circuitry, Instrumentation, Assembly, Testing, Fabrication, etc.
  Can also be used to represent major subsystems
      Examples – Frame, Base, Packaging, Power Source, Controller, Optics, etc.
  Do NOT create one called “To-Do”! There is already a tracker for that!
  Do NOT create them based on people’s names
Use the Filters in the Issues listing to focus on the specific group of issues needed. From the above examples:
  Open To-Do items for Packaging
  Open Bugs in the CAD model
  Open Features in the Software
Lets You Look At / Focus On
the Key Issues

## Slide 12: Defining “Issues” (Tasks)
Trackers: Feature / Bug / To Do
Allows
Filtering
Supports Issue (Task)
Hierarchy
Automatically Keep Team Members Up to Date
Start Date
defaults to ‘today’
Issues without Due Date will NOT be shown on Gantt Chart
Notes: Be specific in describing the issue.
Be action oriented. Be clear what the results are or need to be.
Provide a due date and be sure to assign an owner as soon as possible.

## Slide 13: Using “Issues”
Filters can be defined to focus on specific issues
Note – the above filter has not yet been applied!
Issues With Varying
% Complete
Notes: The filters selected in this screenshot have NOT yet been applied to the Issue list shown
Can sort by any column. Can create complex filters to focus on details – such as all urgent tasks, all tasks assigned to a team member, everything due at a certain version, etc.

## Slide 14: Task-Oriented Project Management Proactively Using Issues
New
Assigned
Closed
Working
Lifecycle of an Issue
Gantt Chart to View and Manage Project Status is
automatically
created from the Issues
Red line indicates ‘today’
Week numbers
Ahead
On Time
Late
Notes: When any team member finds “something”, record it as a New Issue. When it’s reviewed, Assign if to an owner. When a second person determines it is complete, mark it Closed.

## Slide 15: Implementing Your Gantt Chart in EDN
Pre-Plan on Paper or Whiteboard
  Define Versions - Description / Date
  Define Issues - Description / Dates / Owner
    Tie Issues to Versions
    Define Relationships between Issues (Precedes / Follows)
Implement in EDN
  Define Versions
  Define Issues
Update Based on Project Execution

## Slide 16: Turn SOW Deliverables into Versions
Currently Defined Versions
Define New Version
After your Statement of Work is submitted…
Your team should create a Version (NOT an Issue!) for each of the Deliverables you listed on the SOW.

## Slide 17: Creating Categories
Create Categories to help organize the issues. Usually teams create categories that match their Work Breakdown Structure such as:
  Modules
  Subsystems
  Deliverables
Do NOT create a category called “To Do”. There is already a Tracker for that!

## Slide 18: Creating Issues
Clearly define the issue
Reference corresponding forum posting for discussion and artifact collection with link
Be specific!
Be action oriented
Be clear on what the result of the issue is
Provide a Due Date (issues will not be visible on the Gantt Chart view without a due date!)
Assign an Owner, Category, and Version
Add additional team members as watchers
Create Parent / Child relationships to group issues together
Create Follows / Precedes relations to show the sequence of issues (can only be done after creation)

## Slide 19: Managing EDN Issues
New issue
New
0%
Assigned
10%
Working
50%
Ready to Close
100%
Closed
A task (issue) is created (opened)
The task is
assigned to you
A task is created and assigned to team member
A new task (issue) is identified
You start working on the task
You finish the task
Your work is reviewed and approved by PE/CE
Note: When the task status is changed, EDN automatically updates “% Done.”

## Slide 20: Exceptions to Standard Workflow
New issue
New
0%
Assigned
10%
Working
50%
Ready to Close
100%
Closed
Your work is reviewed and
found to be incomplete by your teammate/PE/CE
You create a new task and immediately start the work
You are assigned an existing task and immediately start the work

## Slide 21: Issues and SCRUM
SCRUM | Backlog | In Progress | In Progress | Review | Done
Issue Status | New | Assigned | Working | Completed | Closed
Action | Define a feature (task) | Assign a task to a team member | Work on the task | Review/Inspect the output(s) | Close the issue
The following table maps the SCRUM workflow to the Issue workflow.

## Slide 22: Showing Your Roadmap
There will be a list of the tasks needed to reach this milestone.
Completed tasks will have a line through them.
Nothing has been planned for this milestone yet
List of milestones

## Slide 23: Using the Project Roadmap
Done!
Overall Status of the Version
Version
Can Jump to Any Version
Issues = Tasks
Versions = Milestones
Notes: Quick way to see what’s coming up!

## Slide 24: Project Management Best Practice
On a Regular Basis:
Review open items
  Ensure all items are assigned to an owner
    There should be an owner
    Verify assigned owner is the proper one
  Is there a due date?
  Is Status correct?
  Address problems associated with completing issues
Use Gantt chart view – it’s the industry standard
Try the Calendar view and see if you like it!

## Slide 25: Wikis
Can be used to collaboratively compile information
Should be organized by ‘function’ rather than by ‘team member’
The Capstone Support Wiki has course-wide reference material
Sample of a ‘typical’ project wiki page:
https://designlab.eng.rpi.edu/redmine/projects/capstone-support-dev/wiki/Typical_Home_Page

## Slide 26: Capstone Support Wiki
Two Primary Usages
Shared
Knowledge Base
Creation of Collaborative Documentation

## Slide 27: Creating a New Wiki Page
Go to an Existing Page
Edit
For a new page called “New Page” enter the following (those are square brackets):
    [[New Page]]
That creates a link to the new page.
Save the page
Click on the link you just created
It will take you to the new page in edit mode
Enter your material
Preview to verify layout/format is acceptable
Save the new page
Done!

## Slide 28: Discussion “Forums”
Each Semester Has a Common Set of Forums
  Background Info
  PE/CE Feedback
  Project Management
  Design
  Statement of Work
  Midterm
  Final Deliverables
The Forums Serve as an Electronic Design Notebook
Notes: A place to collaborate on the mid term deliverables and to post and discuss updated versions.
A thread for posting a design artifact and providing feedback (design reviews) as replies.

## Slide 29: Discussion Forums
Measures of Activity
Student Postings are Evaluated for Technical Quality
Notes: Topics / Messages / Last Message give an indication of activity

## Slide 30: Version Control / Subversion
Version Control is Used for:
Software Source Code – All Languages
Microsoft Office / OpenOffice / Latex Documents
Mechanical & Electrical CAD Models
Data
Revision control, also known as version control or source control, is the management of changes to files, documents, and programs.
Adapted from http://en.wikipedia.org/wiki/Revision_control, accessed 3/14/2012
Key Features:
Files stored by Subversion in repositories can be restored if accidentally deleted!
Impossible to overwrite another users files
Can be used to restore project work to your PC after a re-imaging
Can handle large files

## Slide 31: Version Control / Subversion
Figure 1 - Sample Subversion Folder Structure
Sample Folder Structure Suitable for Most Projects
“Tags” are made with / by your PE at the end of the semester as part of the technology transfer of your project. Do NOT work in that folder!

## Slide 32: What Goes Where?
The Electronic Design Notebook has multiple places where information is stored:
  Forums
  Issues
  Wiki
  Repository
See the Capstone Support Wiki for guidance: https://designlab.eng.rpi.edu/redmine/projects/capstone-support-dev/wiki/EDN_FAQ
There is a search box in the upper right corner - use it to find things in your project or the Capstone Support Wiki!

## Slide 33: Best Practices
For forums / issues / wiki – post text directly into the system instead of posting a Word or PDF attachment. Attachments are not searched!
Do not ‘double post’ – do not attach a document AND paste the contents of that document into the post. Do one or the other!
Post information to the EDN instead of sharing via email. Team members, instructors, sponsor/mentors, and people from next semester’s group can not see those emails! And you run the risk of violating your agreement to protect intellectual property.

## Slide 34: Inventory Management
Supports both Resource Books (Book Shelf) and Lab Materials (Device Room)
Shows who currently has the book / equipment
  Pseudo Users “A cabinet 2” and “storage.jec2027” for Storage Locations OR
  Actual person’s name
Books and Equipment
can be signed out

## Slide 35: Monitoring Student Progress
Last Login Date
  Participating Students Will Login Every 1-2 Day
Activity by User
  Timing of Posts
  Relevance / Content / Quality of Posts
  New Material vs. Knowledge Synthesis
  Participating students will have frequent postings of significant technical content
Student Postings are Evaluated for Technical Quality
Notes: Student contributions and participation in this course are evaluated based on the artifacts they produce. This includes physical items, such as devices, and intellectual items which can be seen in everything you post as well as during team meetings / presentations / reviews.

## Slide 36: User Statistics
ID | Forum | Wiki | Repository | Issues |  | 
 |  |  |  | Total | Created | Updates
Student 1 | 11 | 1 | 11 | 11 | 4 | 7
Student 2 | 1 | 1 | 5 | 1 | 1 | 0
Student 3 | 13 | 1 | 18 | 36 | 8 | 28
Student 4 | 20 | 26 | 42 | 31 | 8 | 23
Student 5 | 9 | 5 | 9 | 30 | 10 | 20
We Have Observed a Positive Correlation Between
Posting Quality & Frequency and Team Success
Notes: Simple statistics show who’s active but cannot determine quality from this simple analysis.

## Slide 37: Participation
The EDN is configured to ‘push’ information to you via email. Alternatively, you can chose to diligently visit the site and ‘pull’ the information. (Email preferences available at ‘My Account’ link.)
You each MUST BE AWARE of team progress, status, and problems throughout the semester.
It is every team member’s responsibility to actively participate in the project throughout the semester. This is integrated into the Individual Contribution Factor (ICF), as defined in the course syllabus.

## Slide 38: Conclusions
Collaboration tools play an essential role in The Design Lab’s Capstone Program
Students are evaluated based on making a variety of significant technical contributions and a successful project outcome
Collaborative experiences prepare our students for both academic & industry careers
Productively using the Electronic Design Notebook can increase a team’s level of success