## examples
| Category | Milestone/Deliverable | Notes
Individual benchmarking memos |  | Strong | Class item, internal only
Mechanical Diagrams, Electrical Schematics and Web Layout |  | Medium | of what?
Mechanical CAD, Electrical Simulations, Static Web Page |  | Medium | how different from above?
System Integration and Evaluation |  | Weak | what is the deliverable
Mechanical Final Documentation and Presentation |  | Weak | Demo stronger than Presentation
Mechanical, Electrical, and Web Interface Demonstration |  | Weak | doing what?
Mathematical and Qualitative Design | X
Grippers for robotic arms | X
Standard Operating Procedures | X
Simulation / Prototyping | X
Loading/Unloading | X
Circuit Diagram |  | Weak | of what?
Product Specifications and Functionality |  |  | entire system?
Phase 2 of Design Report |  | Strong | Class item, internal only
Aspect 1 Working Prototype |  | Medium | what is the aspect? Be specific by name
Design of UI |  | Medium | preliminary? Final?
Initial server prototype |  | Medium | of what?
Aspect 2 Working Prototype |  |  | what is the aspect? Be specific by name
Final Server Prototype |  | Medium | demo? Physical object?
Aspect 3 Working Prototype |  |  | what is the aspect? Be specific by name
Final device prototype |  | Weak | doing what? Demo! If not a demo then what?
Final Design Report |  | Strong | Class item, internal only
User and Developer Manual |  | Medium | any draft as deliverable?
Final Prototype Demonstration |  | Strong
Database Layout | X
Demonstrated standalone software |  | Weak | ALL of it? More likely portions - which ones? Doing what?
Documented experiments that can be used as class labs |  | Weak | how many? Do all happen at the same time?
Proposed analytical methods |  | Weak | to do what? Is there a single or multiple topic areas?
The outline of the code |  | Weak | lacks details
Calculation Algorithms | X
Database | X
Experiments | X
User Interface | X
Software System Demo / Housing Prototype |  | Strong
Proposed IoT devices / Specs for housing |  | Strong
Incorporate housing prototype with IoT devices |  | Strong
Demo of IoT/housing devices and Server Software |  | Strong
Full integration of all systems |  | Weak | How do we "know" / see this?
Concept Generation of Reflectors | X
Heat Analysis of Materials | X
CAD Drawings of Parts | X
Working Code for Temperature Sensing |  | Weak | Demo is stronger.
Ray Tracing and Analysis | X
Manufacturing of Parts | X
Testing of Prototype | X
CAD Models | X
Analysis of Survey Data |  | Weak | not specific - what analysis
Define Pedagogical Approach |  | Medium | of what?
Deployment Implementation |  | Weak | not specific / measurable
Feature Iteration: Dynamic Graphics & Usage Stats |  | Strong
Final Version |  | Medium | of what? How confirmed - demo?
Full Data Collection of Customers |  | Weak | maybe - what is "full"?
Full data collection of Test feedback (survey 2) |  | Medium
Midterm |  | Weak
Open Issues for This Semester's Team | X
Polished Website with Planned Features |  | Medium
Program Details and Information Collection |  | Weak | not clear
Survey 1 Report: Feedback of XYZ Difficulties |  | Medium
Survey 2 Analysis: Program Test Feedback |  | Medium
Survey 2 Report: Feedback of Tool's Features |  | Strong
Survey 3 Report: Effectiveness of tool in LMS Quiz |  | Strong
Tutorial Draft N |  | Medium | of what?
User Interface Capability Test |  | Medium
User Manual |  | Medium | draft / final?
Version N of Program |  | Medium
Website with Tutorial and Tabs Features |  | Strong