## F26 proposal
| Project Initiation |  |  |  |  | Project Planning |  |  |  | Preliminary Design |  |  | Project Execution → Final Design | [15 empty] | CHANGES
Week # | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14
On-Site Meeting # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Onboarding Sessions
Project Scoping Sessions
Client Meeting #1 - Kickoff
Technical Memo | [28 empty] | name changed from Benchmarking Memo -> Technical Memo
Individual CE Feedback #1, #2, #3
Needs & Requirements, Use Cases, & User Stories
Safety Training | [28 empty] | moved 1 week earlier, now included on this chart
Team Standard Agreement | [28 empty] | moved 1 week earlier, now included on this chart
Concept Generation & Selection
Client Meeting #2, #3, #4
Technical Progress & Project Mgmt #1
Technical Progress & Project Mgmt #2
Technical Progress & Project Mgmt #3
Technical Progress & Project Mgmt #4
Peer Evaluation
Board of Directors Review | [28 empty] | Returns to schedule
System Architecture Diagram | [28 empty] | Report changed to System Architecture ONLY
Detail Individual Design Report
Individual Technical Demo
Design Showcase
Poster
Final Design Review
Final Design Report
System Evaluation | [28 empty] | relic row/name, changed to Individual Tech Demo
Ethics and Professional Considerations | [28 empty] | now included on this chart
All dates are approximate. Consult syllabus and Task and Due Dates page in Wiki for exact due dates
yellow |  | Graded Assignment
green |  | Student / CE Meeting
orange |  | Team / Client Meeting
blue |  | Guided On-Site Meeting Sessions
grey |  | ICF Factor
purple |  | Draft Submission

## S26
| Project Initiation |  |  |  |  | Project Planning |  |  |  | Preliminary Design |  |  | Project Execution → Final Design
Week | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15
On-Site Meeting # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Onboarding Sessions
Project Scoping Sessions
Client Meeting #1 - Kickoff
Benchmarking Memo
Individual CE Feedback
Needs & Requirements, Use Cases, & User Stories
Safety Training
Team Standard Agreement
Concept Generation & Selection
Client Meeting #2, #3, #4
Technical Progress & Project Mgmt
Peer Evaluation
System Design Report
Detail Individual Design Report
Individual Technical Demo
Design Showcase
Poster
Final Design Review
Final Design Report
System Evaluation
Ethics and Proffesssional Considerations
All dates are approximate. Consult syllabus and Task and Due Dates page in Wiki for exact due dates
yellow |  | Graded Assignment
green |  | Student / CE Meeting
orange |  | Team / Client Meeting
blue |  | Guided On-Site Meeting Sessions
grey |  | ICF Factor
purple |  | Draft Submission