## Slide 1: Welcome to Capstone Design
Introduction and Expectations
First Class

## Slide 2: Revision History
Version | Date | Name | Reason for Changes
0.80 | 7/1/20-8/29/20 | A.Paster | Initial document. Days 1 through 4 are 87% complete. Future days less accurate. Document will be updated as the semester progresses.
0.90 | 8/29/20 | A.Paster | Added urls of key documents and info in Capstone Support Wiki and Repository.
1.0 | 8/30/20 | A.Paster | Link for syllabus questions updated on p.13, table formatting on p.15 Official release of ducument
1.1 | 8/31/20 | B. DeBoer | Specified entry and exit doors for MDL (p. 4) Corrected Shop Room No., added notes requiring PE permission to use shop and requirement for online safety training prior to using shop (p. 6)

## Slide 3: Logistics
All students (in person & remote) should attend class meetings using Webex Teams
  Project Space (ex: GSK Toothpaste Flow)
  Project Engineer Space (ex: Paster-F20-sec1)
This PPT is available on Electronic Design Notebook and will guide the first 10 classes
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/changes/Fall%202020%20Playbook.pptx
Daily Class Agendas
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Class_Agendas

## Slide 4: Covid-19 related challenges
Projects were chosen and scoped to still be possible even in the event RPI semester goes full remote
Off campus and out of country students should strive to stay as synchronous as possible with team meetings and project progress
All course material is available online (EDN)
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki
Nearly all interactions will take place online
  In Class Activities – Webex Team Spaces
    Project Space
    PE Space
  Class time - Webex Project Space or Sub-team Spaces
  Sponsor meetings – Webex meetings
  PE/CE Office hours – Webex private rooms
Classroom
  One-way entry/exit
    Enter @ JEC3332 door (SoE Hub side), exit @ JEC 3232 door
  No use of physical whiteboards. Webex teams has whiteboard functionality
  Chairs stay on X’s at 6 foot separation
  4 additional tables available for smaller 2 person meetings

## Slide 5: Class meeting logistics
Bring laptop, charger, headphones/earbuds to in-person classes
Wear a mask at all times
Teams may wish to record their meetings for any members who are 'absent' or have connection issues.
  ALWAYS encouraged to take meeting minutes and post to EDN for future reference

## Slide 6: Class “location”
Hybrid schedule to reduce campus density
  Your team will meet remote one day and in classroom one day each week
  Approx. 30% of students chose to be all remote
Capstone shop (JEC 2332) will be open 9am-4pm for hands-on work
  Due to COVID, students must request permission to use shop from PE to ensure staffing – walk-ins are not allowed
  Students MUST complete online safety training prior to using shop (PE will send info)
Bounce between Project Space and PE Space
  Agenda and this PPT will continuously remind you of proper location
Notes: PE should remind each team which day they are remote vs in class

## Slide 7: Day 1 Agenda

## Slide 8: RPI Design Lab
Our Mission is to Develop High Performing Engineers by Mentoring Students in Professional and Engineering Design Practices Through Project Based Learning.
NO textbook, NO lecture
It is a Team EXPERIENCE
Guided/assisted by Project Engineer (PE)
Graded/assisted by Chief Engineer (CE)

## Slide 9: Design Lab Team
Project Engineers
Brad DeBoer
Mark Anderson
Aren Paster
Kathryn Dannemann
Shop Technician
Manufacturing Manager
Admin Specialist
Associate Director
Director
Junichi Kanai
Valerie Masterson
Sam Chiappone
Scott Yerbury

## Slide 10
Faculty – Chief Engineers
ISE
MSE
Rahmi Ozisik
Kathryn Dannemann
Mark Embrechts
Cheng Hsu
MANE
Bharat Bagepalli
Matt Oehlschlaeger
Dan Walczyk
Sandipan Mishra
Josh Hurst
Daniel Lewis
Junichi Kanai
Shayla Sawyer
Manoj Shah
Partha Dutta
Kyle Wilt
ECSE
Bill Foley
Sarah Felix
Ali Tajer

## Slide 11: Participation Expectations
Arrive to Class On Time / Stay until class ends
  We encourage use of video
Be present in Class and Team Meetings
  Listen, Engage, Participate
  Not distracted on your Phone or other tasks
3 Credit Hour course mandates:
  4 Hours per week IN class
  5 Hours per week OUT of class
Read communication from Design Lab staff and team mates
  Emails
  Webex chat
  EDN posts

## Slide 12: Capstone is TEAM work not GROUP work
Team Work
  collaborative effort
  peer review
  Student managed
Group Work
  divide and conquer
  low interaction with team
  Supervisor managed

## Slide 13: Grading
Syllabus
  https://designlab.eng.rpi.edu/edn/attachments/download/109925/Common%20Course%20Syllabus.pdf
Tasks and Due Dates
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Tasks_and_Due_Dates
Pose any questions to kanaij@rpi.edu
  Answers will be posted to EDN
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Syllabus_or_Grading_questions

## Slide 14: Behavior Expectations
Q: “How will you interact with your boss and peers in 6 months?”
Let’s start doing this NOW in Capstone Design
  Be Accountable.
    To your teammates, to Chief/Project Engineer, and to project sponsor.
  Be Professional.
  Make your work VISIBLE.
    Post/share as you go. No need to hide from team until its perfect or completely finished.
    Use Electronic Design Notebook (EDN)
Notes: This slide is animated. Shows only the question – PE should ask students and get some responses

## Slide 15: Capstone Orientation Packet
More information
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Confidentiality_Requirements
Director’s Introduction letter | Read Later |  | 
Instructions for electronic signatures in Adobe | Read Later | Reference for last steps | 
Project Description | Should have already read | Reference now | 
Recognition Waiver and Release | Read later | Sign PDF or print and scan | Email to mastev@rpi.edu
Sponsorship Agreement |  |  | 

## Slide 16: Collaboration Logistics
Each team has a Box folder pre-loaded with files
  https://rpi.app.box.com/
  Login using RPI credentials
EVERYONE open “20 min Poster - Webex enabled.pptx” file in PowerPoint Online
  This will allow simultaneous group editing
  (warning/notice) Online version lacks MANY features

## Slide 17: 35 min - Team Ideation Presentation
Time boxed exercise. It will feel rushed, things won't feel complete. THAT'S OK.
You'll want more time. You can't have it. Team must move on.
For EACH section of presentation slides:
2 min
  Individual silent thought on content
  Type thoughts into text editor (Word, Notepad, etc...)
2 min
  Copy answers into shared Team PPT on Box
  Quick discussion of similar, unique, or new answers
Move on to next section of Ideation PPT as a team
PE will send chat messages to PE Space to help remind team to move on to each section of presentation

## Slide 18: 20 min - Team Ideation Presentation Summary
What unique skills does each person bring to the team?
What skills do members share in common?
What specific team or organizational strength will each person contribute?
What team or organizational weakness or areas for growth does each person have?
How can team make best use of each individual’s skills and talents?
Does every team member have a TECHNICAL action item to complete by next class?
  Note: This is something that should happen by end of every class.
Leave above red text for students.
Just don’t get confused by it now, and remember to DELETE THIS BOX

## Slide 19: 15 min - Team Questions
What part of your IED experience do you NOT want to repeat? 4 min
  Personality conflicts
  Time management (ran out of time)
  Unequal division of labor
  Communication breakdown
How ready is your team to move forward on project? (1-10 scale)
  1 min - Pick individual answer
3. Move to PROJECT SPACE, discuss as a team, and come to consensus. 5 min
4. Return to PE SPACE for full class debrief. 5 min
Make this PRETTY

## Slide 20: 5 min – Ticket Out
Design Lab wants your 'immediate' feedback on the course and your experience.
These 'surveys' after many classes will help us help you.
Collected anonymously using Google Forms.
  If you ever want an individual response from PE/CE/Director, be sure to INCLUDE your name.
You can also always use email or Webex to reach out to PE/CE with any questions.

## Slide 21: Out of Class Tasks (what you might call homework, complete BEFORE Class 2)
Complete Class 1 Ticket Out
  https://forms.gle/jDFyUZtew9cb45n7A
Register for EDN – https://designlab.eng.rpi.edu/edn/
  Registration button in upper right hand corner
  Login must be your RCSID (RPI email before the @ symbol)
  Email must be your RPI email
  Bookmark this site. You will use it A LOT for this course.
Post evidence of progress on your project task assignment to team's Box folder as Word file. Filename should be RCSID-topic. Ex: pastea-FreeBodyDiagram.docx
  Web link of research AND summary of why it's important or useful
  Calculations
  Sketch of concept idea
NOTE – These tasks are posted on EDN along with all class agendas
https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Class_Agendas

## Slide 22: Class 2 Agenda

## Slide 23: Capstone Design – Why we do it
What is a "real world experience"?
What is difference between IED and Capstone Design?
Why is Capstone a required course?
What is goal of this course?
What is a successful outcome for
  Project Sponsor?
  Student?
  RPI?
What is the Engineering Design Process?
Notes: Group discussion of all questions

## Slide 24: Design Course Progression
Chart: 
| Instructor | Project | Assessment | multi
Sales | 0.1 | 0.5 | 0.25 | 0.15
Instructor time: prepared lecture and skill instruction
Student project time: research and experimentation
Graded activities: presentation of results, HW/quiz/test
Project work reviewed/graded continuously rather than formally submitted
Instructor Ownership (content)
Student Ownership (project)
Stakeholder is Company/Organization
Student Ownership (project)
Stakeholder is Student Team
Intro Engineering Design
General Coursework
Capstone Design
Chart: 
| Instructor | Project | Assessment
Sales | 0.75 | 0.1 | 0.15
Chart: 
| Instructor | Project | Assessment
Sales | 0.2 | 0.6 | 0.2
On-going Feedback from Instructor

## Slide 25
Instructor Guided Content
Lecture & Lab
Quiz/Test
Structured Activities
Student/team performance feedback
Submit only finished work
Team Guided Content
Meetings (in & out of class)
Design / Build / Test (Engineering Design Process)
Presentations
Peer to peer feedback & review
Iterative design & documentation
Capstone instructor-guided activities will be primarily in first 5 weeks of semester
Chart: 
| General Coursework | Introduction to Engineering Design | Capstone Design
Instructor Guided | 90 | 70 | 40
Team Guided | 10 | 30 | 60
Typical Course Content

## Slide 26: Capstone Design – How We Do It
Solve Open Ended Project by
Applying what you've already learned in 15+ years of courses
  Including re-learning whatever you've forgotten
AND self-learning new skills as needed
Begin the shift from
Engineering Student
Engineer

## Slide 27: Roles and Responsibilities of Team
YOU (students) are OWNER of this project process
Sponsor (company) is OWNER of the project output
Design Lab Instructors are coaches, not teachers
  Offer guidance and help
    Point you to proper book, equation, or process, but students will do the math/analysis to justify their suggested solution
  Project Engineer (PE) – day to day operations
  Chief Engineer (CE) – grading/evaluation

## Slide 28: 15 min - Generate Project Questions
These questions can be about any aspect of the project, but by the end of the class include questions targeted to:
  Customer Needs
  Project Specifications / Technical Requirements
Same inclusive discussion format as yesterday
  2 min. silent question generation
  Then begin copying into Project Questions.xlsx spreadsheet in Box.
  Combine duplicates/similar questions
  Add more to list as you think of them during discussion

## Slide 29
5 min – Classify Questions
Classify all questions generated into one of three categories
  Things team members can research/answer themselves
  Things PE will answer
  Things to ask sponsor during kick-off meeting
40 min – Split between a) Meet w/ PE and b) Assign and work on questions
Project Engineer meets with each team to review categories and confirm/correct. When not meeting with your PE, team members work on researching the A category questions
Team assigns owner to all questions in category A
Add question classification and ownership to spreadsheet
Notes: Point students to other PE/CE/profs as appropriate who are resources for Category A

## Slide 30: 10 min – Full class Wrap up
Information should be complete before documented?
  True or False
It is necessary to document negative results?
  True or False
Teammates share responsibility with PE/CE to offer technical feedback on EDN posts?
  True or False

## Slide 31: Out of Class Tasks (what you might call homework, complete BEFORE Class 3)
Complete Class 2 Ticket Out
  https://forms.gle/EpXvm4hr6xPCtv8T7
Enter contact info to EDN Wiki
Find answer(s) to assigned question(s) & post to Box folder
Watch Customer Needs video (9 min)
  https://mediasite.mms.rpi.edu/Mediasite5/Channel/anderm8winrpiedu-engr-2050/watch/87d950eccc2942038b1d06530e9217841d
Watch Requirements video (11 min)
  https://mediasite.mms.rpi.edu/Mediasite5/Channel/anderm8winrpiedu-engr-2050/watch/96dceab44ae7447d812f5a216afa97cf1d
Identify one Customer Need for your project and translate it into an Engineering Requirement

## Slide 32: Day 3 Agenda

## Slide 33: Sponsor Kick-Off Meeting
Meeting Agenda
  Team introductions to sponsor (name, major, relevant experience/skills)
  Sponsor introduction to team
  Sponsor describes project "in their words“
    History, ultimate and semester goals, deliverables, etc…
  Open Q&A

## Slide 34: Customer Needs/Eng. Requirements
Needs and Requirements workbook.xlsx spreadsheet is in team Box folder
  1st semester projects – start w/ blank template
  Continuing project – start w/ latest version from previous team
  Could use an exercise to ‘remind’ what needs & reqs are

## Slide 35: Prior Presentation (if applicable)
Team should review (outside of class) the final PPT presentation given by previous semester team
  Forums->Final Deliverables
  Repository->Reports->Final Reports
Quickly walk (30 min) PE/CE through slide deck and discuss what you feel previous team would say about:
  Goals
  Accomplishments / Successes
  Challenges
  Next steps
PE/CE will help to clear up confusion and answer any questions current team may have

## Slide 36: Out of Class Tasks (what you might call homework, complete BEFORE Class 4)
Update Needs/Reqs matrix based on feedback (in Box folder)
Choose sponsor liaison
  This person will be the focal point for emails to/from your sponsor. They are not the team's "spokesperson" at meetings, conference calls, in class, etc.
Watch Intro to EDN video (5/min)
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/raw/training/Intro%20to%20the%20EDN.mp4
Read Project Documentation page
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Project_Documentation
Complete the Online Safety Training in Percipio by end of 3rd week
  https://www.percipio.com
  Rensselaer Manufacturing and Prototyping Laboratories-Safety Orientation

## Slide 37: Class 4 Agenda

## Slide 38: CE Meeting with Team
Chief Engineer led discussion of:
  Course grading
  Student expectations
  CE background and experience
  Anything else they’ve said they want to mention?

## Slide 39: Technical Approach

## Slide 40: EDN & Documentation

## Slide 41: Out of Class Task / Action Items:
Complete Class 4 Ticket Out
  https://forms.gle/J6EBfnh2hjTJbPse8
Post to EDN SoW forum
  Updated Needs/Reqs Matrix
  Bulleted list of Technical Approaches
Complete the Online Safety Training in Percipio by end of 3rd week
  https://www.percipio.com
  Rensselaer Manufacturing and Prototyping Laboratories-Safety Orientation

## Slide 42: Class 5 Agenda

## Slide 43: Statement of Work Exercise
10 min – Break into 3 groups
  Long Term Objectives (1-5+ years, from Customer Perspective)
  Current Semester Objectives (3 months!)
  Deliverables (Be S.M.A.R.T.!)
10 min - Team review – Long Term and Current Semester Objectives
15 min - Team review – Deliverables
55 min
  PE/CE review of Deliverables
  Team development of Dates and Engineering Tools and Methods
Create threads in Statement of Work Forum for notes on each section

## Slide 44: Out of Class Task / Action Items:
Complete Class 5 Ticket Out
  https://forms.gle/WcGzPoJYMSpJrepQ8
Wordsmith and polish SoW
Post Statement of Work to EDN - SoW Forum prior to class 6

## Slide 45: Class 6 Agenda

## Slide 47: Out of Class Task / Action Items:
Continue technical work
Post progress to Design Forum threads
Add deliverables from Statement of Work into EDN as milestones (versions)
Brainstorm 6 individual tasks which need to be accomplished to reach project goals

## Slide 48: Class 7 Agenda

## Slide 49: Out of Class Task / Action Items:
Create draft of Status Report topics
  Template - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Templates_and_Forms
Create agenda for 30 mins of Class 8
Add tasks identified in Gantt Chart exercise into EDN as Issues
Attend Comm+D workshop on PPT/posters(Weds 2/12) ??

## Slide 50: Class 8 Agenda

## Slide 51: Out of Class Task / Action Items:
Address any feedback on status update PPT
Sponsor liaison should email PPT to sponsor 24 hours prior to call
Continue technical work
Post progress to Design Forum thread(s)
Student Team should now be creating individual project tasks

## Slide 52: Class 9 Agenda

## Slide 53: Out of Class Task / Action Items:
Class 9 Ticket Out
  https://forms.gle/fahNCHu9zFo7Qeze6
Upload poster draft to EDN - PDR Forum
Continue technical work
Post progress to Design Forum thread(s)
Student Team should now be creating class agendas and individual project tasks