## Slide 1: Welcome to Capstone Design
Introduction and Expectations
First Class

## Slide 2: Revision History
Version | Date | Name | Reason for Changes
2.0 | 1/4/2021 | M. Anderson | Cloned from last version of 2020 Fall.
2.1 | 1/4/2021 | M. Anderson | Starting updates from team discussion, playbook feedback notes, etc.
2.2 | 1/7/21 | A. Paster | Added CE introduction to Day 1 Student Meet & Greet added as Out Of Class after Day 1
2.3 | 1/12/21 | A. Paster | Tip to update playbook before each class added to all agenda slides
2.4 | 1/15/21 | A. Paster | Phases of Design Report added p 41 Small grammar/formatting changes throughout Playbook ‘Every project is different’ slide moved to Day 3 (previously Day 6) p 49 Webex/Meeting Tips slide added p 9 PE instructions added to p36 Safety Training reminder improved Comm+ D slide removed
2.5 | 1/15/21 | A. Paster | ”template“ removed from Report & Poster filenames
2.6 | 1/15/21 | A. Paster | Needs & Reqs Matrix -> Workbook Double check agreement of Agenda schedules and Out of Class Tasks w/ Wiki
2.7 | 1/21/21 | Paster | Updated CE pictures Updated Ticket Out links
2.8 | 1/22/21 | A. Paster | Updated Syllabus link p6
2.9 | 1/25/21 | A. Paster & J. Kanai | Day 1 Agenda slide moved EDN links updated for course materials

## Slide 3: Revision History - continued
Version | Date | Name | Reason for Changes

## Slide 4: Revision History - continued
Version | Date | Name | Reason for Changes

## Slide 5: Link to Agendas
Class 1
Class 2
Class 3
Class 4
Class 5
Class 6
Class 7
Class 8
Class 9
Pro Tip – Current Out of Class Tasks are listed ONE page before next class’s agenda

## Slide 6: Day 1 Agenda
* CE will jump into Project Team Space Time for their 5 min personal introduction
*

## Slide 7: Logistics
All students (in person & remote) should attend class meetings using Webex Teams
  Project Space (ex: GSK Toothpaste Flow)
  Project Engineer Space (ex: S21-sec1-Paster)
This PPT is available on Electronic Design Notebook (EDN) and will guide the first 9 classes
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/raw/playbook/2021%20Spring%20Playbook.pptx
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH class meeting.
Daily Class Agendas
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Class_Agendas

## Slide 8: Covid-19 related challenges
Projects were chosen and scoped to still be possible even in the event RPI semester goes full remote
Off campus and out of country students should strive to stay as synchronous as possible with team meetings and project progress
All course material is available online (EDN)
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki
Nearly all interactions will take place online
  In Class Activities – Webex Team Spaces
    Project Space
    PE Space
  Class time - Webex Project Space or Sub-team Spaces
  Sponsor meetings – Webex meetings
  PE/CE Office hours – Webex private rooms
Classroom
  One-way entry/exit
    Enter @ JEC3332 door (SoE Hub side), exit @ JEC 3232 door
  No use of physical whiteboards. Webex teams has whiteboard functionality
  Chairs stay on X’s at 6 foot separation
  4 additional tables available for smaller 2 person meetings

## Slide 9: Class meeting logistics
Bring laptop, charger, headphones/earbuds (for best Webex audio) to in-person classes
Wear a mask at all times
Teams may wish to record their meetings for any members who are 'absent' or have connection issues.
  ALWAYS encouraged to take meeting minutes and post to EDN for future reference

## Slide 10: Webex/Meeting Tips
Be productive for meetings.
  Have a written agenda, posted into the EDN Project Management folder
  Keep meeting minutes for ALL team Webex sessions and post to the Project Management forum on EDN
Divide workload among team members and create EDN Issues to document and track
Webex chat will not be archived, so it's important to document results & discussion in the Forums and the Repository as appropriate
Although Webex can be great for socialization, we would like to encourage productive meetings to reduce Webex burnout

## Slide 11: Class “location”
Hybrid schedule to reduce campus density
  Your team will meet remote one day and in classroom one day each week
  Approx. 30% of students chose to be all remote
Capstone shop (JEC 2332) will be open 9am-4pm for hands-on work
  Due to COVID, students must request permission to use shop from PE to ensure staffing – walk-ins are not allowed
  Students MUST complete online safety training prior to using shop (PE will send info)
Bounce between Project Space and PE Space
  Agenda and this PPT will continuously remind you of proper location in slide footer
Notes: PE should remind each team which day they are remote vs in class

## Slide 12: RPI Design Lab
Our Mission is to Develop High Performing Engineers by Mentoring Students in Professional and Engineering Design Practices Through Project Based Learning.
NO textbook, NO lecture
It is a Team EXPERIENCE
Guided/assisted by Project Engineer (PE)
Graded/assisted by Chief Engineer (CE)

## Slide 13: Design Lab Team
Project Engineers
Brad DeBoer
Mark Anderson
Aren Paster
Kathryn Dannemann
Shop Technician
Manufacturing Manager
Admin Specialist
Associate Director
Director
Junichi Kanai
Valerie Masterson
Sam Chiappone
Scott Yerbury

## Slide 14: Faculty – Chief Engineers
MANE
Bharat Bagepall
Matt Oehlschlaeger
Dan Walczyk
Sandipan Mishra
Josh Hurst
Junichi Kanai
Shayla Sawyer
Manoj Shah
Partha Dutta
Kyle Wilt
Sarah Felix
Ali Tajer
ECSE
ISE
MSE
Ishwara B. Bhat
Agung Julius
Dylan Rees
Karthik Panneerselvam
Mark Embrechts
Al Wallace
Rahmi Ozisik
Kathryn Dannemann
Daniel Lewis
Dave Duquette

## Slide 15: Participation Expectations
Arrive to Class On Time / Stay until class ends
  We encourage use of video
Be present in Class and Team Meetings
  Listen, Engage, Participate
  Not distracted on your Phone or other tasks
3 Credit Hour course mandates:
  4 Hours per week IN class
  5 Hours per week OUT of class
Read communication from Design Lab staff and team mates
  Emails
  Webex chat
  EDN posts

## Slide 16: Capstone is TEAM work not GROUP work
Team Work
  collaborative effort
  peer review
  Student managed
Group Work
  divide and conquer
  low interaction with team
  Supervisor managed

## Slide 17: Grading
Syllabus
  https://designlab.eng.rpi.edu/edn/attachments/download/109925/Common%20Course%20Syllabus.pdf
Tasks and Due Dates
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Tasks_and_Due_Dates
Pose any questions to kanaij@rpi.edu
  Answers will be posted to EDN
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Syllabus_or_Grading_questions

## Slide 18: Behavior Expectations
Q: “How will you interact with your boss and peers in 6 months?”
Let’s start doing this NOW in Capstone Design
  Be Accountable.
    To your teammates, to Chief/Project Engineer, and to project sponsor.
  Be Professional.
  Make your work VISIBLE.
    Post/share as you go. No need to hide from team until its perfect or completely finished.
    Use Electronic Design Notebook (EDN)
Notes: This slide is animated. Shows only the question – PE should ask students and get some responses

## Slide 19: Capstone Orientation Packet (email)
More information
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Confidentiality_Requirements
Director’s Introduction letter | Read Later |  | 
Project Description | Should have already read | Reference now | 
Instructions for electronic signatures in Adobe | Read Later | Reference for last steps | 
Recognition Waiver and Release | Read later | Sign PDF or print and scan | Email to Design Lab administrator mastev@rpi.edu
Sponsorship Agreement |  |  | 

## Slide 20: Collaboration Logistics
Each team has a Box folder pre-loaded with files
  https://rpi.app.box.com/
  Login using RPI credentials
EVERYONE open “20 min Poster - Webex enabled.pptx” file in PowerPoint Online
  This will allow simultaneous group editing
  (warning/notice) Online Office version lacks MANY features of standalone program

## Slide 21: 30 min - Team Ideation Presentation
Time boxed exercise. It will feel rushed, things won't feel complete. THAT'S OK.
You'll want more time. You can't have it. Team must move on.
For EACH section of presentation slides:
2 min
  Individual silent thought on content
  Type thoughts into text editor (Word, Notepad, etc...)
2 min
  Copy answers into shared Team PPT on Box
  Quick discussion of similar, unique, or new answers
Move on to next section of Ideation PPT as a team
PE will send chat messages to PE Space to help remind team to move on to each section of presentation

## Slide 22: 20 min - Team Ideation Presentation Summary
What unique skills does each person bring to the team?
What skills do members share in common?
What specific team or organizational strength will each person contribute?
What team or organizational weakness or areas for growth does each person have?
How can team make best use of each individual’s skills and talents?
Does every team member have a TECHNICAL action item to complete by next class?
  Note: This is something that should happen by end of EVERY class.

## Slide 23: 5 min - Team Meeting
Choose a 30-60 min time for team to meet before next class
  www.WhenIsGood.net works well
  NOT RECOMMENDED to use this time every week for the full team. That’s what class time is for. Instead use this time for occasional needed planning meetings, or for smaller sub groups to meet about project.
MUST REACH DECISION TODAY! You have a group assignment to complete before next class.

## Slide 24: 10 min – Questions about IED and Capstone Readiness
What part of your IED experience do you NOT want to repeat? - 4 min
  Personality conflicts
  Time management (ran out of time)
  Unequal division of labor
  Communication breakdown
How ready is your team to move forward on project?
1 (low) - 10 (high) scale
1 min - Pick individual answer
Move to PROJECT SPACE, discuss as a team, and come to consensus - 5 min
Return to PE SPACE for full class debrief - 5 min

## Slide 25: 5 min – Ticket Out
Design Lab wants your 'immediate' feedback on the course and your experience.
These 'surveys' after many classes will help us help you.
Collected anonymously using Google Forms.
  If you ever want an individual response from PE/CE/Director, be sure to INCLUDE your name.
Please Complete Ticket Out Today or Tomorrow
You can also always use email or Webex to reach out to PE/CE with any questions.

## Slide 26: Out of Class Tasks (what you might call homework, complete BEFORE Class 2)
Complete Class 1 Ticket Out
  https://forms.gle/x4v8t6ECTpdk7SYh8
Register for EDN – https://designlab.eng.rpi.edu/edn/
  Registration button in upper right hand corner
  Login must be your RCS ID (RPI email before the @ symbol)
  Email must be your RPI email
  Bookmark this site. You will use it A LOT for this course.
Use out of class team meeting to start team building
Student Team Introductions
    Major, hometown
    Interests, clubs/sports, experience related to project topic
    Co-op, internship, summer job
    Pet, favorite ice cream flavor
Post evidence of progress on your project task assignment to team's Box folder as Word file. Filename should be RCSID-topic. Ex: pastea-FreeBodyDiagram.docx
  Web link of research AND summary of why it's important or useful
  Calculations
  Sketch of concept idea
NOTE – These tasks are posted on EDN along with all class agendas
https://designlab.eng.rpi.edu/edn/projets/capstone-support-dev/wik/Capstone_Class_Agendas

## Slide 27: Class 2 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH class meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion

## Slide 28: 30 min - Capstone Introduction and Expectations part 2

## Slide 29: Capstone Design – Why we do it
What is a "real world experience"?
What is difference between IED and Capstone Design?
Why is Capstone a required course?
What is goal of this course?
What is a successful outcome for
  Project Sponsor?
  Student?
  RPI?
What is the Engineering Design Process?
Notes: Group discussion of all questions

## Slide 30: Design Course Progression
Chart: 
| Instructor | Project | Assessment | multi
Sales | 0.1 | 0.5 | 0.25 | 0.15
Instructor time: prepared lecture and skill instruction
Student project time: research and experimentation
Graded activities: presentation of results, HW/quiz/test
Project work reviewed/graded continuously rather than formally submitted
Instructor Ownership (content)
Student Ownership (project)
Stakeholder is Company/Organization
Student Ownership (project)
Stakeholder is Student Team
Intro Engineering Design
General Coursework
Capstone Design
Chart: 
| Instructor | Project | Assessment
Sales | 0.75 | 0.1 | 0.15
Chart: 
| Instructor | Project | Assessment
Sales | 0.2 | 0.6 | 0.2
On-going Feedback from Instructor

## Slide 31
Instructor Guided Content
Lecture & Lab
Quiz/Test
Structured Activities
Student/team performance feedback
Submit only finished work
Team Guided Content
Meetings (in & out of class)
Design / Build / Test (Engineering Design Process)
Presentations
Peer to peer feedback & review
Iterative design & documentation
Capstone instructor-guided activities will be primarily in first 5 weeks of semester
Chart: 
| General Coursework | Introduction to Engineering Design | Capstone Design
Instructor Guided | 90 | 70 | 40
Team Guided | 10 | 30 | 60
Typical Course Content

## Slide 32: Capstone Design – How We Do It
Solve Open Ended Project by
Applying what you've already learned in 15+ years of courses
  Including re-learning whatever you've forgotten
AND self-learning new skills as needed
Begin the shift from
Engineering Student
Engineer

## Slide 33: Roles and Responsibilities of Team
YOU (students) are OWNER of this project process
Sponsor (company) is OWNER of the project output
Design Lab Instructors are coaches & mentors, not teachers
  Offer guidance and help
    Point you to proper book, equation, or process, but students will do the math/analysis to justify their suggested solution
  Project Engineer (PE) – day to day operations
  Chief Engineer (CE) – grading/evaluation

## Slide 34: 15 or 20 min - Generate Project Questions
These questions can be about any aspect of the project, but by the end of the class include questions targeted to:
  Customer Needs
  Project Specifications / Technical Requirements
Same inclusive discussion format as first class
  2 min. silent question generation
  Then begin copying into Project Questions.xlsx spreadsheet in Box.
  Combine duplicates/similar questions
  Add more to list as you think of them during discussion

## Slide 35
Split between
a) 20 min Project Engineer Meeting
      Project Engineer meets with each team:
        to check on team status / welfare
        to discuss project, review question & categories, and confirm/correct. When not meeting with your PE, team members generate/discuss questions.
b) 15 min Classify and Assign Questions
      Classify all questions generated into one of three categories
        Things team members can research/answer themselves
        Things PE will answer
        Things to ask sponsor during kick-off meeting
      Team assigns owner to all questions in category A
      Add question classification and ownership to Box spreadsheet
Notes: Point students to other PE/CE/profs as appropriate who are resources for Category A

## Slide 36: 15 min – Engineering Documentation
Topics
  What is Documentation?
  Why bother?
  How is it done in Capstone?
PE note:
  Let group answer 1st two questions
  Then run through next few slide to see if anything was not suggested
  Then discuss 3rd question

## Slide 37: What is Documentation? Engineering Documentation?
Living record of your work
  Evolution of your product/design is traceable
  Your work (experiment) is reproducible
  Your work can be understood by others and why you did it that way

## Slide 38: Why Document?
Extension of your memory
  Who, What, When, Where, Why, How
  So that others can collaborate and continue the work
  Facilitates teamwork
  So that others can review/understand your work
Legal ramifications
  Contractual/legal defense
  Patent application
Efficiently and Effectively move the project forwards

## Slide 39: Capstone Course Policies
Electronic Design Notebook - REQUIRED for all collaboration
GroupMe – team logistics
When Is Good – meeting scheduling
Not Permitted
  Slack or Discord for chatting
  Google Drive for file storage
  Google Suite for document creation
  Other cloud based tools for any use (schematics, mind maps, drawings, analysis, etc…)
Webex Teams is good for chat and live meetings, but project documentation MUST be transferred to EDN Forum or Repository.
  Simple/easy solution is to never put it on Webex to begin with.

## Slide 40: What Tool Will You Use?
Electronic Design Notebook (EDN)
  Integrated Project Management
  Threaded Communication by topic, rather than a single unorganized stream
  IP protection
  Grading - accountability and visibility
  Secure access to team and sponsor
  Backed up daily !
  The EDN software may not be the PERFECT choice, but nothing is.
  It meets the Design Lab's needs better than the alternatives*.
  * https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Why_Electronic_Design_Notebook_is_the_ONLY_choice

## Slide 41: What Should I Document?
Everything
  Research, web links, notes
  Interviews and observations
  Ideas, concepts, sketches, charts, diagrams
  Calculations
  Purchases - components models, vendors, cost
  Analyses – technical and non-technical
  Experiments, debugging, tests
  Hypothesis, procedures, equipment used, steps taken, data, results
  Future work/ideas

## Slide 42: 10 min – Full class Wrap up
Information should be complete before documented?
  True or False
It is necessary to document negative results?
  True or False
Teammates share responsibility with PE/CE to offer technical feedback on EDN posts?
  True or False

## Slide 43: Out of Class Tasks (what you might call homework, complete BEFORE Class 3)
Complete Class 2 Ticket Out
  https://forms.gle/JCqdyLoLm7SzbyRZ6
Post personal contact info (name, major, RPI email, phone #) to EDN Background Info Forum
Find answer(s) to assigned question(s) & post to Box folder
Watch Customer Needs video (9 min)
  https://mediasite.mms.rpi.edu/Mediasite5/Channel/anderm8winrpiedu-engr-2050/watch/87d950eccc2942038b1d06530e9217841d
Watch Requirements video (11 min)
  https://mediasite.mms.rpi.edu/Mediasite5/Channel/anderm8winrpiedu-engr-2050/watch/96dceab44ae7447d812f5a216afa97cf1d
Identify one Customer Need for your project and translate it into an Engineering Requirement
For ongoing projects, review prior semesters’ final presentations in accordance with PE instructions for class discussion in Class 3/4

## Slide 44: Day 3 Agenda
Over the course of Days 3 & 4 – All teams will complete the following:
Sponsor Kickoff Meeting
CE meeting with team
Customer Needs & Requirements - development and review
Review previous Final Presentation – ongoing projects only
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH class meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion

## Slide 45: 15 min - Engineering Design Process
We will use the Engineering Design Process
This is INTENTIONALLY a quick refresher of the Design Process as covered in IED.
This may help you understand what it means and how your team can apply it to your Capstone project
If you remember it well – please help your team mates!

## Slide 46: Engineering Design Process
Today is Day Three of class
Let’s look at steps ONE & TWO
Customer Needs
Engineering Requirements
This Design Process and terminology is taught in IED at RPI

## Slide 47: 10 mins - Customer Needs & Engineering Requirements Example
Discuss a Vehicle
  What are Customer Needs?
  Translate those to Engineering Requirements
With Needs and Reqs in mind - an informed customer could go to a dealership and talk about “product specifications” and choose the ‘right’ car for themselves

## Slide 48: User Stories
Alternative method to Needs/Reqs to document how users/customers will interact with a system, website, program
User Story (who, what, and why of system use)
  As a [type of user], I want to [perform some task] so that I can [achieve some goal].
Acceptance Criteria (how to judge success)
  Given that [some context], when [some action is carried out], then [a set of observable outcomes should occur].

## Slide 49: All teams are in a different place
Project Age
  New project
  Continuing project
Goal
  New product/process
  Improvement of existing product/process
  Investigation of new technology
  System integration
Product Life cycle
  Research and Development
  Growth
  Repair & Maintenance
Team
  Multidisciplinary vs single discipline
  Remote vs on-campus
That’s OK and expected.
The Engineering Design Process still applies.

## Slide 50: 30 min - CE Meeting with Team (Class 3 or 4)
Chief Engineer led discussion of:
  Course
    Course grading
    Student expectations
  CE background and experience
  Project impressions

## Slide 51: 45 min - Customer Needs & Engineering Requirements Generation
Needs and Requirements workbook.xlsx spreadsheet is in team Box folder
Fill out based on team’s current (uninformed impression) of project
  This is first pass. Don’t worry that answers are not complete or verified by sponsor.

## Slide 52: 45 min - Sponsor Kick-Off Meeting
Meeting Agenda
  Team introductions to sponsor (name, major, relevant experience/skills)
  Sponsor introduction to team
  Sponsor describes project "in their words“
    History, ultimate and semester goals, deliverables, etc…
  Open Q&A

## Slide 53: 30 min - Prior Presentation (if applicable)
Team should review (outside of class) the final PPT presentation given by previous semester team
  Forums->Final Deliverables
  Repository->Reports->Final Reports
Quickly walk PE/CE through slide deck and discuss what you feel previous team would say about:
  Goals
  Accomplishments / Successes
  Challenges
  Next steps
PE/CE will help to clear up confusion and answer any questions current team may have

## Slide 54: Out of Class Tasks (what you might call homework, complete BEFORE Class 4)
Update Needs/Reqs Workbook based on feedback (in Box folder)
Post class notes taken during PPT review to Project Management Forum
Choose sponsor liaison
  This person will be the focal point for emails to/from your sponsor. They are not the team's "spokesperson" at meetings, conference calls, in class, etc.
Watch Intro to EDN video (5 min)
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/raw/training/Intro%20to%20the%20EDN.mp4
Read Project Documentation page
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Project_Documentation
Complete the Online Safety Training in Percipio by end of 3rd week
  https://www.percipio.com
  Rensselaer Manufacturing and Prototyping Laboratories-Safety Orientation
  NOT required for
    Fully remote students
    Local students without campus access

## Slide 55: Class 4 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH class meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion

## Slide 56: 55 Min - Project Work
Refine Needs and Requirements Spreadsheet
  Needs
    Ensure all known Customer Needs are documented
  Requirements:
    Associate with appropriate Customer Need(s)
    Identify Measurements and Units (quantitative)
    Ensure that Requirements are detailed and prioritized
    Identify Applicable Engineering Standards
Refine/Develop Follow-Up Questions for Sponsor
  If Team has already had Sponsor Meeting, what new questions have been identified as a result?
    Clearly document and send to Sponsor, copy PE
Background Research/Benchmarking
  Discuss/document work done to date
  Identify/document additional benchmarking needs

## Slide 57: 30 min - CE Meeting with Team (Class 3 or 4)
Chief Engineer led discussion of:
  Course
    Course grading
    Student expectations
  CE background and experience
  Project impressions

## Slide 58: Out of Class Task / Action Items:
Complete Class 4 Ticket Out
  https://forms.gle/eUVnT8KSCReEV8fp6
Update Needs/Reqs Workbook - post to EDN Design forum
Complete the Online Safety Training in Percipio by end of 3rd week
  https://www.percipio.com
  Rensselaer Manufacturing and Prototyping Laboratories-Safety Orientation
  NOT required for
    Fully remote students
    Local students without campus access

## Slide 59: Class 5 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH class meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion

## Slide 60: 30 min - Documentation & EDN Usage
You should have already watched EDN video and read Documentation Wiki page
  Intro to EDN video (5 min)
    https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/raw/training/Intro%20to%20the%20EDN.mp4
  Project Documentation page
    https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Project_Documentation
Where to post your work
How to create post (which buttons/links on EDN)
Notes: Need to add some show not tell to these slides
How do you currently organize information:
On your desk
-on your PC
In text messages
In emails
Within an organization, e.g. fraternity / sorority, sports teams, clubs, etc.

## Slide 61: Where to put information?
Forums Tab
Technical Work
Task Assignments
Work through quick examples using EDN

## Slide 62: How to post
New Message
Forums
Live demonstration of making a forum post

## Slide 63: 10 min - Engineering Tools and Methods
  What techniques, software, calculations will be used to address the problems in front of team? Ex:
  Mechanical aspects – Free Body diagram, torque measurement
  Software – flow chart of system control loop, storyboard of user input
  Process – conduct customer interviews of toddler caregivers, create Standard Operating Procedure for system startup and calibration

## Slide 64: 10 min - Statement of Work Introduction 60 min - Statement of Work Exercise
https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/changes/template%20documents/Design%20Report.docx
10 min – Break into 3 groups (meet in subteam spaces A/B/C)
  Long Term Objectives (1-5+ years, from Customer Perspective)
  Current Semester Objectives (3 months!)
  Deliverables (Be S.M.A.R.T.!)
Shift back to Team Space
10 min - Team review – Long Term and Current Semester Objectives
15 min - Team review – Deliverables
20 min
  PE/CE review of Deliverables
  Team development of Dates for Deliverables and Engineering Tools and Methods
Create threads in Statement of Work Forum for notes on each section

## Slide 65: Phases of the Design Report
In ALL cases, the file name and location remains the same:
“working/Reports/Design Report and Poster/Design Report.docx”
Phase 1
Statement of Work
Phase 2
Preliminary Design Report
Phase 3
Final Report
Week 4
Midterm
End of Semester

## Slide 66: Out of Class Task / Action Items:
Complete Class 5 Ticket Out
  https://forms.gle/pCSbvzc4oMb4Kzkg6
Wordsmith and polish Statement of Work
Post Statement of Work (Phase 1 of Design Report.docx) to EDN Repository prior to class 6 in the folder:
  working/Reports/Design Report + Poster
Complete the Online Safety Training in Percipio by end of 3rd week
  https://www.percipio.com
  Rensselaer Manufacturing and Prototyping Laboratories-Safety Orientation
  NOT required for
    Fully remote students
    Local students without campus access

## Slide 67: Class 6 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH class meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion

## Slide 68: 10 min – What’s a Concept?
Return to car example discussed last class
What were the needs? The requirements?
What concepts address the needs/reqs identified?

## Slide 69: 65 Min - Concept Generation
Similar inclusive plan as previous exercises using Box document
5 min – Individually silently generate any concept to solve/address project needs/reqs
10 min – Add concepts to Concept Generation Spreadsheet.xlsx in Box
15 min – Organize list by topic
  Eliminate duplicates
  Add extra ideas you think of right now or are inspired by others ideas
35 min – Group discussion
  Explain further to improve group understanding – if necessary
  Look for missing/unaddressed needs –think of concepts to address them
  Look for lone concepts – think of alternative ideas

## Slide 70: 5 min – Create Forum Threads
Concept topics ARE the key discussions and work areas for the team
Create Design Forum threads for each topic
  Use these thread to post explanation, sketches, calculations, etc…
  Reply to team mates posts to move idea forwards and advance project

## Slide 71: 20 min – Project Work
Go to Team Space
Work on project
Someone should take notes of meeting discussion
Post to Forums –> Project Mgmt
  NOT as Word document, simply as plain text in Forum post.

## Slide 72: Out of Class Task / Action Items:
Continue technical work
Post progress to Design Forum threads
Add deliverables from Statement of Work into EDN as milestones (versions)
Brainstorm 6 individual tasks which need to be accomplished to reach project goals
Complete the Online Safety Training in Percipio by end of 3rd week RIGHT NOW
  https://www.percipio.com
  Rensselaer Manufacturing and Prototyping Laboratories-Safety Orientation
  NOT required for
    Fully remote students
    Local students without campus access

## Slide 73: Class 7 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH class meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion

## Slide 74: 10 min - Project Planning
To improve odds of success having a plan ALWAYS helps.
Let’s talk about building a house.
How is ‘plan’ communicated?
What are the milestones?
How is timing/scheduling/order important?

## Slide 75: 95 min - ‘Post It Note’ Project Planning Exercise
10 min – (individually silently) generate list of TEN tasks which team must accomplish to meet deliverables
(PE has/will preload with Deliverables from SoW)
10 min – enter tasks in the Gantt Chart PPT.pptx in Box
Create 1 text box for each task
Choose a personalized fill color for your entries
Position tasks appropriately along week by week calendar
60 min – Group organization of tasks
Add missing tasks, remove duplicates
Organize by subsystem or milestone
15 min – Re-assign ownership (by color) to ensure everyone has work throughout semester

## Slide 76: Out of Class Task / Action Items:
Create draft of Status Update PPT topics
  Template - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Templates_and_Forms
Create agenda for 60 mins of Class 8
EDN Gantt Chart Creation
  Create Versions for each deliverable
  Add your personal tasks identified in Gantt Chart exercise as Issues
Complete the Online Safety Training in Percipio by end of 3rd week RIGHT NOW !!
  https://www.percipio.com
  Rensselaer Manufacturing and Prototyping Laboratories-Safety Orientation
  NOT required for
    Fully remote students
    Local students without campus access

## Slide 77: Class 8 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH class meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion

## Slide 78: Out of Class Task / Action Items:
Address any feedback on Status Update PPT
Sponsor liaison should email PPT to sponsor 24 hours prior to call
Continue technical work
Post progress to Design Forum thread(s)
Student Team should now be creating individual project tasks

## Slide 79: Class 9 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH class meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion

## Slide 80: 15 min – Preliminary Design Review Introduction
Opportunity to share information and receive feedback
  Tradeshows
  Conference
  Investor pitch
Tell a cohesive story to introduce project
  Audience is educated (profs and RPI students), but may know NOTHING about your topic
  2-3 mins to establish big picture background and history
You WILL be interrupted with questions
Use the poster as a guide
Logistics
  Presentations via Webex NOT in-person
  Students not presenting should join as audience for OTHER projects

## Slide 81: 95 min – Poster Creation
Open Poster.pptx in Box in PPT Online
10 mins – Divide into 3 groups, shift to sub-Spaces on Webex Teams, and work on initial slides. Content can be pulled from Statement of Work.
  Purpose
  Past Work and/or Project History
  Semester Objectives/Requirements
40 mins – As a full team discuss Technical Approach, Results and Accomplishments to Date
30 mins – Move on to Next Steps and Plan
15 mins – Begin assembly of content onto single slide (pg 8)

## Slide 82: Out of Class Task / Action Items:
Class 9 Ticket Out
  https://forms.gle/At5axsgWRajmq2Gu5
Upload poster draft to EDN - PDR Forum
Continue technical work
Post progress to Design Forum thread(s)
Student Team should now be creating agendas for each class meeting and individual project tasks