## Slide 1: The Statement of Work
The Design Lab at Rensselaer

## Slide 2: The Statement of Work - SoW
What Is It?
Written Shared Understanding of the Project
Why Do We Use One for Capstone?
Used to Define Projects and Help Manage Scope
Commonly Used in Industry
When Is It Created for a Capstone Project?
Approximately Week 4
https://searchitchannel.techtarget.com/definition/statement-of-work-SOW

## Slide 3: The Process
https://merlinone.com/mistakes-generating-statement-of-work/
Download and Review the Design Report Template
Note Sections Required for SoW
Consider How Those Sections Relate To Your Project
For Each Section – As You Work
Remove any sample text / instructions
Fill in the appropriate information
Some Sections May Require More Discussion Than Others
This is Preliminary and WILL Be Revised During the Project
All Team Members Proofread the Entire Document
Notes: [BDD]
Audio cut early

## Slide 4: These Design Report Sections = SoW
The Statement of Work is simply Phase 1 of the Design Report
You Will Add The Other Sections Later In the Semester
Notes: [BDD]
May want text equating “Phase 1” to SoW - done
Need to make clear that Executive Summary is not part of SoW – I missed that trimming the table! Thanks!

## Slide 5: Where / How ?
Section | General Guidance / Information Source
List of Figures and Tables | Automatically Created by Using Word Captions
Revision History | Loosely Keep Track of Changes
Glossary | Start this ASAP & Keep Adding
1. Introduction | New Writing
2. Project Objectives & Semester Objectives | Leverage The Initial Project Description
3. Engineering Tools and Methods | From Your Earlier Working Session
References | Start this ASAP & Keep Adding! Do NOT do this last!
Appendix A: Initial Deliverables and Dates | From Your Earlier Working Session
The file name and location in your Repository always remains the same:
“working/Reports/Design Report and Poster/Design Report.docx”
Notes: [BDD]
Executive Summary is only completed for the Final Design Report (Phase 3) - fixed
Audio mentions checking into Subversion, but students may not yet have been trained? RELOOK !!!!!!! But we did this last semester…

## Slide 6: Section 1 - Introduction

## Slide 7: Helpful Hints - Introduction
What Is an Introduction?
“An introduction introduces readers to the report and not necessarily, or only minimally, to the subject matter. "Introduction" does not equal "background"; it may contain some background but only minimally. “ https://www.prismnet.com/~hcexres/textbook/introds.html
“In technical writing, the information provided in the introduction is vital to helping the reader see the need for the information being presented. It helps set the context for the topic being discussed in the document. Just as with the news story on potential meat shortages, introductions help the readers open their minds to the ideas you're presenting in your document. Introductions provide a preview of the document's content, while explaining why the information is needed. Introductions acquaint the audience with the topic by introducing the background and explaining how this specific topic fits into the larger field of study.” https://study.com/academy/lesson/introductions-of-technical-documents.html
This Photo by Unknown Author is licensed under CC BY-SA-NC

## Slide 8: Section 2 - Project Objectives & Semester Objectives

## Slide 9: Helpful Hints - Background and Motivation
Included in Section 2 - Project Objectives & Semester Objectives
May come from: Industry / Academia, Your sponsor, Previous capstone teams
Start with your project description
Change for new information (if any) from your sponsor meeting(s), PE, CE
This Photo by Unknown Author is licensed under CC BY
Notes: [BDD]
I think that I would put the Section in the Slide Title?
  Should the be “Helpful Hints – Introduction”, or “Helpful Hints: Section 1 – Background and Motivation”, etc.?
  First Bullet – I think that this should be Section 1?

## Slide 10: Helpful Hints - Long Term Objectives and Customer Payoff
Included in Section 2 - Project Objectives & Semester Objectives
aka “The Big Picture”
Timeframe: 2-5 Years after this semester
What will your customer do with your results?
Assume your work may need to be combined with other developments at RPI or Sponsor
How will your results facilitate better products, higher profits, contributions to society, etc.?
This Photo by Unknown Author is licensed under CC BY-SA-NC

## Slide 11: Helpful Hints - Current Semester Objectives
Included in Section 2 - Project Objectives & Semester Objectives
aka “The Little Picture”
If yours is an on-going project, summarize the project history first so that it is easy for the readers to understand why you chose the semester objectives.
Do NOT simply repeat the generic design process.
Capture the valuable results that you will produce and deliver to your customer in this one-semester course.
Include specific commitments by your team
What will delight your sponsor?
Be project specific, not generic.
This Photo by Unknown Author is licensed under CC BY-NC
20xx
Notes: [BDD]
Audio cuts out early (not sure how early?) Interesting as I have no control over that… the “cuts” from slide to slide are done by PowerPoint. May need to actually pause speaking between slides so it knows where/when to split the audio.

## Slide 12: Section 3 – Engineering Tools and Methods

## Slide 13: Helpful Hints - Engineering Tools and Methods
Section 3 of the Design Report
Provide specific information on the technical aspects of work.
Convince the reader that the team has the technical know-how required to execute the project.
Do not include project management approach details unless they specifically relate to how the team will deliver their work. Check with your PE.
See Example On Next Slide
https://www.engineering.com/story/5-skills-hiring-managers-look-for-in-engineering-grads

## Slide 14: Helpful Hints - Engineering Tools and Methods
Project Area | Tools and Methods
Software | Iteratively releasing code for sponsor feedback Flow chart of system control loop Storyboard of user input Pseudocode for embedded software
Mechanical | Free Body diagram - relationship of force vectors Torque measurements on the shaft to determine maximum system loading Finite element analysis (FEA) for maximum deflection under expected load
Process | Conduct customer interviews of toddler caregivers Create Standard Operating Procedure for system startup and calibration Discrete Time Simulation using ARENA for material flows for factory layout
Examples

## Slide 15: Appendix A – Initial Deliverables and Dates

## Slide 16: Helpful Hints – Initial Deliverables and Dates
Found in Appendix A
Do not list course items, e.g. Preliminary Design Document, sponsor visits, etc.
Include completion of specific intermediate project accomplishments
Analysis, experiments, design drawings or fabrication of parts
Confirm deliverables are tangible items.
Be S.M.A.R.T.
Be specific to your project, rather than generic.
Deliverables are the outputs of the tasks, not the tasks themselves. E.g.
  Task - Research competitors' products.
  Deliverable - A report on competing products.
Deliverables should relate to your Current Semester Objectives
This Photo by Unknown Author is licensed under CC BY-NC
Notes: [BDD]
Audio cut early (and may have started late?)

## Slide 17: Things to Keep In Mind
Stay S.M.A.R.T.
Proofread
Do not rename the file! Keep “Design Report.docx”
Avoid flowery prose. Be concise and technically focused. Be sure all terms are clear or defined.
Incorporate feedback from PE/CE/sponsor
Use Our Checklists as a Self-Evaluation Rubric
Look at the Rubric - https://designlab.eng.rpi.edu/svn2/capstone-support-dev/Rubrics
https://experteditor.com.au/proofreading-services/
https://grad.tamu.edu/Blog/Blog/April-2018/The-Powerful-Tool-Checklist
Notes: [BDD]
Audio appears to have started late

## Slide 18: Additional Resources
The Project Management Institute, https://www.pmi.org/
  Training Materials
  Certifications
  Publisher of “The Project Management Book of Knowledge”
Ulrich & Eppinger / Ulrich, Eppinger and Yang
  Product Design and Development – Project Management chapter in the IED Textbook
Capstone Support Wiki
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Statement_of_Work
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Gantt_Charts__Project_Management