## Slide 1: The Statement of Work Building a House Example
The Design Lab at Rensselaer

## Slide 2: The Statement of Work - SoW
This presentation will use the example of a family contracting to have a new home built for them.
It assumes that the Contractor has already interviewed the family to gather their needs and has already turned those into requirements, possibly with the help of an architect.
An SoW is now needed to form the contract between Contractor and the Family.

## Slide 3: The Key Sections
Based on the Capstone Design Report Template, we will focus on Sections:
2. Project Objectives & Semester Objectives
3. Engineering Tools and Methods
This Will Be the Majority Of the Writing

## Slide 4: Background and Motivation
The Smith family is seeking a new home to replace their undersized current home.
There are two adults and two growing children currently under the age of 5. They have one medium sized dog, a Labrador Retriever named “Spot”.
Mrs. Smith works from home and would like a dedicated home office space.
The neighborhood currently consists of single family one or two story frame homes. All roofs appear to be asphalt shingles.
Based on the typical NY Capital District weather, only a few homes have a pool. The Smith’s are interested in the ability to add one in a year or two.

## Slide 5: Long Term Objectives and Customer Payoff
The Smith’s long term vision is to raise their children through at least their high school graduation in this home. They do not consider this their “forever” home, i.e. they would not necessarily plan to retire in this home – or location!
The home and property should support their family as the children grow up.
They are not currently planning to expand their family with either additional children or other family members (e.g. no aging parents to accommodate).

## Slide 6: Current Semester Objectives
The home needs to be ready to occupy at the end of construction
The landscaping must be complete and the planted items (e.g. lawn) should have successfully started growing or taking root.
A clear area for a well-placed future backyard pool should be allocated and clear of trees / other large plantings.
Notes: [BDD]
- First bullet doesn’t really make sense – isn’t that statement kind of implied? Should “end of construction” be a date?

## Slide 7: Engineering Tools and Methods
Project Area | Tools and Methods
Construction | Blueprints will be approved by architect and Family Framing will be of wood Poured concrete foundation with sump pump to maintain drainage Roof trusses will be pre-engineered and pre-fabricated
Landscaping | Grading to keep water away from foundation Grass will be planted around the house as decoration and erosion control Shrubs will be used in the front yard to provide privacy Existing or new trees will be used for shade Select trees will be removed from backyard to create recreation space
Legal | Contractor is responsible for obtaining all required local / state permits Contractor is responsible for obtaining a Certificate of Occupancy at completion
Unique to the Building Trades
Notes: [BDD]
- I’m concerned that the “Tools and Methods” here are highly biased towards methods, and that the example therefore may not really prompt the students in the way that we want. As I recall, we used the house example for the project planning exercise, but before that, we used a car. Would a car perhaps be a better example here, as we could better call out tools and methods that our students would realistically utilize?

## Slide 8: Initial Deliverables and Dates
Deliverable | Date
Start of Project | 1/1/2020
Foundation Complete | 2/1/2020
Exterior Framing & Roof Trusses Complete | 3/15/2020
Exterior Sheathing / Roof Covering Complete | 4/15/2020
Interior Framing Complete | 5/1/2020
Electrical and Plumbing Rough Work Landscaping Complete | 5/15/2020
Drywall Complete | 5/30/2020
Interior & Exterior Painting Complete | 5/15/2020
Electrical and Plumbing Finish Work | 6/1/2020
Building Inspection / Certificate of Occupancy | 6/5/2020
Available for Occupancy | 6/10/2020
For a Commercial / Industrial project, a third column would typically indicate the payment plan.
This does not apply for Capstone!
For Capstone, we are looking for only 5-7 Deliverables.
A more aggressive and common building timeline would be 2-4 months!
Notes: [BDD]
Interior Painting is supposed to be complete before drywall….
If we’re only looking for 5-7 deliverables, we shouldn’t give an example with 11