## Slide 1: Project Name
Identifier (ex: Status Update #2, Final Presentation): 11/15/2016
Team members (Name, Major / Graduation Date)
Sponsor Mentors: (name)
Project Engineer: (name)
Chief Engineer: (name)
Sponsor Logo

## Slide 2: Creating a Meaningful Project Status Update
Goals:
Communicate your project status AND provide a technical design review
How:
Hit as many items as appropriate from the Making Strong PowerPoint Presentations page on the Capstone Support Wiki
https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Creating_Strong_PowerPoint_Presentations

## Slide 3: This File Is:
An example of the typical content for a status report / project design review
While NOT an exact ‘recipe’ for all teams / projects, talk to your PE before changing!
A PowerPoint “template”. The footers are properly defined. Do not edit them!
Questions – see your Project Engineer EARLY!

## Slide 4: Goal for Project Status Updates
To Effectively and Rapidly Communicate the Overall Progress, and how that matches or deviates from planned schedule of your Project, to your Project’s:
Sponsor
Chief Engineer
Project Engineer

## Slide 5: Goal for Project Design Reviews
To Effectively and Rapidly Communicate and Receive Feedback on the Overall Design to your Project’s:
Sponsor
Chief Engineer
Project Engineer

## Slide 6: The Steps - Read All These Slides First!
Create a Project Management Forum thread with the meeting date. Do ALL collaboration on the slides in that thread. Do NOT use non-EDN resources for that, i.e. no chat, texting, Google, etc.
Copy this template to a new file name.
  Name the files using a “YYYY-MM-DD-Status Report.pptx” convention where YYY-MM-DD is the planned meeting date. The files sort easily by date this way.
  Save in your working copy of the repository on your PC. Do NOT add a file version numbers – the repo already handles that!
Replace the instructions with your content
Review the instructions on EDN at: https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Creating_Strong_PowerPoint_Presentations (contents may change!)
Review and Edit your content! Commit to the repository as everyone edits
Share your slides with your Project Engineer for review, well in advance (at least 2-3 days) of your scheduled conference call / meeting
Modify your content based on that feedback
Email to Sponsor at least 24 hours before call / meeting!

## Slide 7: Typical Conference Call Agenda
Update from Sponsor
  Needed at first meeting - let sponsor speak first!
  May be needed during the semester. Can be moved elsewhere in the agenda as appropriate
Project Status
  A summary of results to date – based on your Statement of Work/Schedule
  Updates per Subsystem / Major Work Areas
Demonstrations
  if applicable / appropriate / available
  live if possible, have pre-recorded video just in case!
Answers / Decisions Needed from Sponsor
Next steps
  Summary of work to be accomplished between now and the next call
Schedule or confirm the next call
Your FIRST Slide Deck Will Be a Simplified Version of This

## Slide 8: Project Info
Before diving into the status, be sure to have some introductory material, such as:
Purpose
Key Needs / Goals
System Architecture
Etc.

## Slide 9: Project Status
Health | Deliverable | Plan Due Date | Planned / Actual Completion Date | Status Explanation
 | Circuit Design Complete | 9/23 | 10/23 | Explain WHY it’s late and what you are doing about that!
 | Software Prototype Demo |  |  | This milestone may be late – but has not yet happened. Explain what you will do to bring it back in line
 | Mechanical Testing Done |  |  | This milestone is in ‘good shape’ and there are no apparent obstacles to completion
Sometimes called a Project “Dashboard”
‘Deliverables’ can be the milestones listed in your Statement of Work
Keep the Legend!
Legend
Green = Good
Yellow = At Risk
Red = In Trouble

## Slide 10: Explanations of Late Items
The next slides should address the problems seen in the Project Status slide

## Slide 11: Circuit Design Complete
Provide details associated with the work needed to reach this milestone.
May be detailed OR team may need to break this down by subsystems
MUST indicate HOW the team will achieve THIS milestone.
It’s not about the team’s organization, subsystems, etc. but about how the team will achieve the project goals on time.

## Slide 12: Software Prototype Demo
Repeat these detail slides as needed for the milestones coming in the next 2-4 weeks

## Slide 13: Project Design Review
The next slides can now address the technical progress / subsystems / accomplishments.
Provide context, i.e. overall system block diagram(s), architecture, etc.
Avoid “diary mode”, e.g. we did this, this and this. Focus on results / accomplishments
Show rather than tell, i.e. pictures/graphs over words

## Slide 14: Mechanical Testing Done
The team does NOT need to repeat this pattern for ALL milestones, just the ones in the next 2-4 weeks
For this example – what does this look like? Graphs, charts, diagrams. Provide expected results and actual results & analysis of differences.

## Slide 15: Answers / Decisions Needed
This is MUCH more actionable and urgent than a slide titled just ‘Questions’. This slide alerts everyone that project progress is at risk until / unless this information is received.
LIST YOUR ITEMS ON THE SLIDE !!!
Your Project Engineer should review and approve this list (actually the ENTIRE slide set) BEFORE your sponsor sees it! This OFTEN / USUALLY requires an in person discussion.

## Slide 16: Current Challenges
Challenge | Status | Planned Resolution
These are neither questions nor decisions. These are items the team needs to alert everyone to.
Note the use of a table to make this easier to present and to digest.
Be sure your Status indication is clear/obvious.
Consider adding a column for “severity” then sort by that to keep hot items at the top.
Teams – Identify your ONE key takeaway from this and put that here on the slide. Like this, in a box, at the bottom of the slide.

## Slide 17: Don’t Forget!
Follow the guidelines for Creating Strong PowerPoint Presentations found on the Capstone Support wiki
Use it as a checklist of important items
https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Creating_Strong_PowerPoint_Presentations