## Slide 1: Welcome to Capstone Design
Playbook for Classes 1 to 9
Scaffolded Meetings

## Slide 2: Link to Agendas
Class 1
Class 2
Class 3
Class 4
Class 5
Class 6
Class 7
Class 8
Class 9
#Pro Tip – Current Action Items are listed ONE page before next class’s agenda

## Slide 3
Multidisciplinary Capstone Design
ECSE 4900 Electrical & Computer Systems Engineers
ISYE 4270 Industrial Engineers
MANE 4260 Mechanical Engineers
MTLE 4920 Materials Engineers

## Slide 4: Class 1 Agenda
Team Development /
Design Process Refresher
Administrative Tasks
Project Work
TD
A
P

## Slide 5: 5 min - Logistics
This PowerPoint is available on Electronic Design Notebook (EDN) and will guide the first 9 meetings
  Playbook - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Playbook
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH class meeting to get the latest info.
Daily Meeting Agendas
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Daily_Agendas

## Slide 6: Design Lab Mission
Develop High Performing Engineers by Mentoring Students in Professional and Engineering Design Practices Through Project Based Learning.

## Slide 7: Capstone Design Transition
NO textbook, NO lecture
It is a Team EXPERIENCE
It is a mostly “flipped” experience
Guided/assisted by Project Engineer (PE)
Graded/assisted by Chief Engineer (CE)

## Slide 8: Capstone Design: Practice Engineering in Safe Environment
Initial Cover letter and Resume
New Employee Packet from your Project Engineer
Design Lab Support Staff
Project Engineers and Chief Engineers
Students in a Course 
Consulting Engineering Team Solving a Client Problem

## Slide 9
Design Lab
Engineering Team
New hire

## Slide 10: New Employee On-Boarding Day 1 Agenda
Team Development /
Design Process Refresher
Administrative Tasks
Project Work
TD
A
P
Class 1 Agenda

## Slide 11: Faculty – Chief Engineers
MANE
ECSE
MSE
ISYE
Junichi Kanai
Kathryn Dannemann
Prabahakar Neti
Indika Perera
Muhsin Celik
Casey Hoffman
Nima Ahmadi
Paul Chow
Alex Patterson
Rahmi Ozisik
Fred Willett

## Slide 12: Design Lab - Core Values
At the Design Lab we will :
Work with people of diverse backgrounds, skills, and perspective
Create an inclusive and equitable team environment
Act with Professionalism and Respect

## Slide 13: Participation Expectations
Arrive to meetings on time. Stay until meeting ends.
Be present in all meetings.
Listen, Engage, Participate.
Focus on the Project.
Minimize Distractions
(phone, other tasks)

## Slide 14: Work Expectations
Your new position involves:
  4 Hours per week of on-site work
  5 Hours per week of off-site work
    Individual technical work & team meetings
Document all of progress and results
Read communication from Design Lab staff and teammates
  Emails
  Webex chat
  EDN posts
Please respond in a timely manner!

## Slide 15: Capstone is More TEAM work than GROUP work
Team Work
  Collaborative effort
  Interactive -peer review
  Team member managed
Group Work
  Divide and conquer
  Low interaction with team
  Supervisor managed

## Slide 16: Work Expectations
Q: “What expectations do your boss and peers have at work?”
Let’s start doing this NOW in the Design Lab.
  Be Accountable.
    To your teammates, to Chief/Project Engineer, and to project Client.
  Be Professional.
  Make your work VISIBLE.
    Post/share as you go. Please do not “hide” it from team until its perfect or completely finished.
    Use Electronic Design Notebook (EDN)
Notes: This slide is animated. Shows only the question – PE should ask students and get some responses

## Slide 17: Design Lab Communications & Documentation Policies
Written capstone communications are permitted using ONLY Design Lab tools:
  The EDN
    Native EDN posts, MS Office files, CAD, etc.
  Webex
Use of any other cloud-based service, such as Google Drive/Docs/Sheets/Slides, GroupMe, Discord, Slack, Draw.io, etc. is FORBIDDEN
Although supported by campus, RPI Box and RPI Onedrive are also FORBIDDEN
Scheduling services such as WhenIsGood & When2Meet are acceptable for setting up meetings but must not contain any technical information
This Helps Protect Against Unauthorized Access And
Provides Equal Access To All Team Members

## Slide 18: Accountability Step #1
More information on Sponsorship Agreement and Confidentiality
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Confidentiality_Requirements
You all received the New Employee Packet via email:
Director’s Introduction letter
Project Description - Will guide your work today
Instructions for electronic signatures in Adobe
Recognition Waiver and Release - SIGN & return by end of day
Sponsorship Agreement - SIGN & return by end of day
MANDATORY for all employees to SIGN & return by end of day

## Slide 19: 25 mins - Ice Breaker
Desired Outcomes
  Prepare everyone for collaborative engineering team performance by helping create a relaxed environment where everyone can share ideas and participate more fully
  Build rapport among the engineering team members

## Slide 20: The Process…
Break into pairs within your team – if your team has an odd number of members, one group should include three members
Answer the prompt for the first question using Slido – 1 minute
Pair off and Share Responses with your partner & discuss – 2 minutes
Go around the team and each person introduces their partner – name & skill – 5 minutes
Review the full word cloud & discuss – 2 minutes
Answer the prompt for the first question using Slido – 1 minute
Pair off and Share Responses with your partner & discuss – 2 minutes
Go around the team and each person introduces their partner – name & skill – 5 minutes
Review the full word cloud & discuss – 2 minutes

## Slide 21: Ice Breaker Activity
Insert Slido material here!!!
Three slides
Note that both sides will access same Slido. NOT a problem!

## Slide 22: 40 min – Staff Introduction & Project Launch
Chief Engineer (CE) & Project Engineer (PE) Introductions
  Both individuals will stop by to meet with the team
Project Description Review
  If you have not read the document yet, NOW is your chance. You need that information to do the next step effectively!
Generate Project Questions

## Slide 23: 5 min - Meet with Project Engineer
  Project Engineer meets with each team:
    Explain the PE Role
    Check on team status / welfare
    Team member introductions
    When not meeting with your PE or CE, team members generate/discuss questions.

## Slide 24: 5 min - Meet with Chief Engineer
  Chief Engineer meets with each team:
    Explain the CE role
    Check on team status / welfare
    Team member introductions
    Discuss project impressions
    CE’s background/experience
    When not meeting with your PE or CE, team members generate/discuss questions.

## Slide 25: 10 min – Review Project Description
    Re-Read Project Description
    PE is available to answer any fundamental project questions the Team may have
      - Write these questions on the Whiteboard

## Slide 26: Engineering Design Process - Scaffolding Progression
This Design Process and terminology was learned previously in IED
Days 1-5
Days 3-5
Day 7
Day 6 – Project Statement and Objectives, Eng. Tools and Methods
Days 8-9 – Project Planning and Communication Skills
You are here!

## Slide 27: 20 min - Generate Project Questions
This exercise is intended to help you build on what you learned in IED
  IED project was created by team, and therefore easier to identify Needs, as the team was the client
  In capstone you are working for an external client and must practice understanding customer needs by interviewing client and asking questions
  Based on the Project Description and your engineering knowledge, what questions can you ask the client to better understand and document their needs?
Notes: Begin discussion here about building on what was learned in IED as opposed to IED refresher
Yogi Berra – If you don’t know where you are going, you’ll end up somewhere else

## Slide 28: 20 min - Generate Project Questions
These questions can be about any aspect of the project, but by the end of today MUST include questions targeted to functionality and goals
Refer to the Project Description as needed
Write individual questions on separate Post-It notes - ONE question per Post-It.
Combine duplicate / similar ideas
Discuss, collaborate, and add to the list of questions
Take photo of board BEFORE end of meeting to preserve the list for Day 2 activity.
Post photo to Webex project space

## Slide 29: Question Prompts
  Functionality
  Performance
  Quality
  Usability
  Accessibility
  Reliability
  Durability
  Availability
  Manufacturability
  Maintainability
  Environmental Impact
  Interfaces
Potential topic areas for generating questions:

## Slide 30: 5 min – Team-Building Retreat
During the second week, there will be an off-site, peer-led, Team-Building Retreat
Retreat Goals:
  Build positive foundations of teamwork and communication.
  Foster motivation and accountability within teams.
  Enhance leadership, working together, and getting to know each other.
  Understand the importance of eye contact and active listening.

## Slide 31: Team-Building Retreat
Location – Meet in the JEC 3222
Schedule - Three options:
  Wednesday 01/17 6:00-8PM
  Saturday 01/20 10:00AM-NOON
  Sunday 01/21 10:00AM-NOON
Attendance is expected (and incentivized with a little treat)
  Goal is to have entire or majority of team at one session
  If entire team can’t make same session, individuals will work with other teams during the event
Notes: Pic: http://www.entrepreneur-resources.net/theres-no-i-in-team-let-your-company-identity-grow-naturally

## Slide 32: Team-Building Retreat
Action Required!
  Determine which session works best for team
  Each individual must register by Close of Business (COB) on Tuesday, 01/16/24 at: Capstone S24 LEAP Training Sign Up - Google Sheet
Notes: Pic: http://www.msimarinesolutions.com/uploads/3/2/3/0/32309061/img-2216.jpg

## Slide 33: 10 min – Wrap-up
Each day of the scaffolded meetings will end with a wrap-up and discussion of next steps
Team Engineers (YOU) are expected to complete Action Items/Meeting Prep work between in-class meetings to be prepared and make efficient use of meeting time.
Notes: No different from industry

## Slide 34: Wrap-up
On Day 2, teams will utilize the work started today and continued off-site.
  Questions will be categorized then answered by team members, PE, or client.
    Establishing a strong list of questions aids in having a productive Project Kickoff meeting.
    Helping team members to begin answering questions about their project.
  Prepare for Project Kickoff meetings with clients to take place during Day 3 or 4 (project-dependent).

## Slide 35: Action Items / Meeting Prep (previously called homework, to be completed BEFORE Meeting 2)
Team Development / Design Process Refresher
Identify time and register for Team Building Retreat at
  Capstone S24 LEAP Training Sign Up - Google Sheet
Administrative Tasks
Register for EDN – https://designlab.eng.rpi.edu/edn/
  Registration button in upper right-hand corner
  Login must be your RCSID (RPI email before the @ symbol)
  Email must be your RPI email
  Bookmark this site. You will use it A LOT for this course.
Watch Capstone Introduction & Expectations – Part 2 video (7 Min)
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/raw/training/Capstone%20Introduction%20and%20Expectations%20Part%202.mp4
T/D
A
Project Technical Work
Re-read the Project Description with Meeting 1 Question Generation exercise in mind
Post list of project questions to team’s Webex General space
Each team member add TWO additional project questions to team’s Webex General space for further discussion in Day 2
P

## Slide 36: Day 2 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH meeting.
Playbook - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Playbook
Team Development /
Design Process Refresher
Administrative Tasks
Project Work
TD
A
P

## Slide 37: Engineering Design Process - Scaffolding Progression
This Design Process and terminology was learned previously in IED
Days 1-5
Days 3-5
Day 7
Day 6 – Project Statement and Objectives, Eng. Tools and Methods
Days 8-9 – Project Planning and Communication Skills

## Slide 38: 10 min – Design Lab Expectations Q&A
Action Item was to watch 1 video (Capstone Introduction & Expectations – Part 2)
Ask me 1 or 2 QUESTIONS about content!
What is difference between IED and Capstone?
Who ‘owns’ your project – team, PE, CE, Client?
What is role of team members in Capstone?
What is role of PE?
What is role of CE?
Notes: Day 2
IED vs CD – Not re-learning IED material – building on what was learned
IED – Becoming an Engineer
CD – Be an Engineer
Owner – Students
Role of Students – Solve an open-ended complex problem by applying good engineering practices
Role of PE – Assist students by day to day operations
Role of CE - Evaluation

## Slide 39: Action Item / Meeting Prep Categories
P
Project Technical Work
  Contribute directly to project progress and deliverables
  ALL project documentation & planning – notes, reports, analysis, Gantt chart
  Background research, design, prototyping, testing
T/D
A
Team Development / Design Process Refresher
  Forming, Storming, Norming, Performing
  Sequence of design artifacts – Needs & Requirements, Concepts, Decision Matrix
Administrative Tasks
  Onboarding - Legal paperwork, Safety training
  Design Lab Logistics

## Slide 40
Chart: Activity Breakdown by Day (mins)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Project technical work (P) | 40 | 75 | 45 | 70 | 75 | 95 | 90 | 90 | 90 | 90
Team development / Design process refresher (T) | 30 | 0 | 55 | 30 | 0 | 10 | 10 | 15 | 15 | 15
Administrative tasks (A) | 40 | 35 | 10 | 10 | 35 | 5 | 10 | 5 | 5 | 5
Project Works Starts on Day 1!

## Slide 41: 35 min - Team Ideation Exercise
Goal
Accelerate the Forming stage of the engineering team development process by establishing: - common understanding of the project - the team members’ background and skills
Time boxed exercise: It will feel rushed, things won't feel complete. THAT'S OK.
You'll want more time. You can't have it. Team must move on – the team has deadlines to meet!
Process
For EACH section of Ideation poster:
2 min
  Individual silent thought on content
  Write thoughts on Post-It Notes, one per Post-It
2 min
  Place Post-Its onto poster sheet
  Quick discussion of similar, unique, or new answers
Move on to next section of Ideation Poster as a team
Completed Team Ideation Poster
Notes: Tuckman’s stages of team development – learned in IED, practiced and built on in CD

## Slide 42: Team Ideation Poster Creation Activities
We Are (5 min + 1 min)
Write your project name at top.
We Imagine Our Project to Be (2 min + 2 min)
What Can Go Wrong? (2 min + 2 min)
What are some potential challenges (2 min + 2 min)
What classes and/or experience can you call on to help with this project? (2 min + 2 min)
What technical problems need to be solved to successfully complete this project? (2 min + 2 min)
Notes: Hand out “We Are” cards just before that step
Potential Challenges include societal, financial, environmental, technical, ethical, etc.

## Slide 43: 15 min - Team Skill Assessment
Shared by 2+ Team Members
________________
________________
Unique Skills
_______________
_______________
Skill Gaps
_______________
_______________
Please Create a Word Document Based on your Team Poster
Post the MS Word document to EDN Project Management forum thread by end of today’s meeting!

## Slide 44: 30 min - Classify and Assign Questions
  Classify all project questions generated during Day 1 meeting and Action Items into one of three categories
    Things team members can research/answer themselves
    Things PE will answer
    Things to ask Client during kick-off meeting
  Team assigns owner to all questions in category A
  Add question classifications and ownership to Word document
  Chief Engineer & Project Engineer review questions & classification
  Post document to EDN Forum by end of meeting – Project Mgmt thread
Does every team member have a TECHNICAL action item to complete by next meeting?
  Note: Team should assign action items at end of EVERY meeting.

## Slide 45: 10 mins – Communication & Documentation Policies
Electronic Design Notebook - REQUIRED for all collaboration
Webex – Team Chat
WhenIsGood or When2Meet – meeting scheduling
Not Permitted
  Slack, GroupMe, or Discord
  Google Drive
  Google Docs/Sheets/Slides
  Other cloud-based tools for any use (schematics, mind maps, drawings, analysis, etc…) e.g., diagrams.net, etc.
  RPI Box, RPI Onedrive, RPI Sharepoint
  Texting, Instagram, WhatsApp, etc. for ANY project technical content
Webex is good for chat and live meetings, but project documentation should start on and stay in the Electronic Design Notebook (EDN) Forum or Repository.
  Simple/easy solution is to never put it on Webex (or elsewhere) to begin with.

## Slide 46: Electronic Design Notebook (EDN)
  Integrated Project Management
  Threaded Communication by topic, rather than a single unorganized stream
  IP protection
  Performance Evaluation - accountability and visibility
  Secure access to team and Client
  Backed up daily !
  The EDN software was chosen as it currently meets the Design Lab’s needs better than the alternatives*.
  * https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Why_Electronic_Design_Notebook_is_the_ONLY_choice

## Slide 47: What Should I Document?
Everything
  Research, web links, ALL NOTES *
  Interviews and observations
  Ideas, concepts, sketches, charts, diagrams
  Calculations
  Purchases - components models, vendors, cost
  Analyses – technical and non-technical
  Experiments, debugging, tests
  Hypothesis, procedures, equipment used, steps taken, data, results
  Future work/ideas
* On-site / off-site – ALL meetings & individual work
Although everyone should take notes, there should be a designated note taker for each meeting.
Thou shalt document ALL
thy work

## Slide 48: 5 min - Team Standards Agreement Intro
According to concepts in organizational behavior, there are five stages of team development (Tuckman’s Model, 1964): forming, storming, norming, performing and adjourning
In high performing teams a Team Standards Agreement is often generated to establish procedures and roles in order to move the team more quickly into the performing stage
A Team Standards Agreement will be generated off-site by each team before Day 6
  The Team Standards Agreement shall be posted to your team’s EDN Wiki page in accordance with the instructions in the following document: https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Team_Standards_Agreement
Completed Agreement should be posted to Wiki by START of Day 6

## Slide 49: 5 min – Wrap-up
Days 3 and 4 include:
  Teams’ initial client
  Continuing development of Client Needs
  Beginning translating Client Needs into Engineering Requirements
  Review of prior team’s presentation (if applicable)
Client Needs and Engineering Requirements:
  Are not easy and require practice to do well!
  Guide your project throughout the semester

## Slide 50: Wrap-up
As we move from Day 2 to Day 3, the transition from Onboarding to Project Scoping accelerates
  Off-site teambuilding activity (Onboarding) still to come
  Defining Client Needs (Scoping) has already begun
Employee Onboarding
Project Scoping

## Slide 51: Action Items / Meeting Prep (previously called homework, to be completed BEFORE Day 3)
Team Development / Design Process Refresher
Read The Engineering Design Process Refresher.pptx in preparation for meeting 3 discussion
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/raw/training/The%20Engineering%20Design%20Process%20Refresher.pptx
Watch Customer Needs video (9 min)
  https://mediasite.mms.rpi.edu/mediasite/Play/87d950eccc2942038b1d06530e9217841d
Watch Engineering Requirements video (11 min)
  https://mediasite.mms.rpi.edu/mediasite/Play/96dceab44ae7447d812f5a216afa97cf1d
Team Standards Agreement due by Day 6
Identify time and register for Team Building Retreat at https://docs.google.com/spreadsheets/d/1YyuAUceBjjqBNjeVwXmJcqnEKxf7gu66obY1jszcvQQ/edit#gid=0
Administrative Tasks
Watch EDN Guidance for Action Items - Initial Postings Video (7.5 min)
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/raw/training/EDN%20Guidance%20for%20Out%20of%20Class%20Tasks%20-%20Initial%20Postings.mp4
Post personal contact info (name, major, RPI email, phone #) to a Project Management Forum thread in accordance with the Initial Postings Video. First team member creates the thread, other members reply to add their info.
T/D
A
Project Technical Work
Find answer(s) to assigned question(s) & post to new thread titled “Day 2 Questions and Answers” in EDN Background Info Forum
Identify one Customer Need for your project and translate it into an Engineering Requirement. Post to new thread in EDN Design Forum titled “Initial Needs and Requirements”. Leverage the Team Ideation Poster! First member creates the thread, other members reply to add their thoughts.
For ongoing projects, review prior semesters’ final presentations in accordance with PE instructions for discussion during Meeting 3 or 4
  PPT should be in last semester’s Repository or Final Deliverables Forum on EDN
  First team member - create new thread in EDN Background Info titled "Questions about project"
  Rest of team - respond to thread with questions you have about project
P

## Slide 52: Day 3 & 4 Activities
Over next 2 on-site meetings - All teams will complete the following:
  Project Kickoff Meeting
  CE meeting with team
  Client Needs & Requirements - development and review
  Review previous Final Presentation - ongoing projects only
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH on-site meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion
Playbook - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Playbook

## Slide 53: Day 3 Agenda
Notes: PE Notes
Continuing projects should follow Track C or D
New projects can follow A, B, E or F
Track A or C on Day 3 should follow track A or C on Day 4
Track B, D, or E on Day 3 should follow track B or D on Day 4

## Slide 54: Engineering Design Process - Scaffolding Progression
This Design Process and terminology was learned previously in IED
Days 1-5
Days 3-5
Day 7
Day 6 – Project Statement and Objectives, Eng. Tools and Methods
Days 8-9 – Project Planning and Communication Skills

## Slide 55: 30 min – Meet with CE (Day 3 or 4)
Chief Engineer led discussion of:
  Performance Evaluations – aka Course grading
  Team member expectations
    Group discussions
    Project Documentation on EDN
    Action Items
  CE background and experience
  Project impressions
  Team Standards Agreement
Notes: Cover these slides in front of class VERY BRIEFLY. They are a reference for the 4 activities which will be done this meeting and next meeting (Day 3 & 4). Students will/can/should open the Playbook and read when they are going through the activities.

## Slide 56: 45 min - Customer Needs & Engineering Requirements Generation
Needs and Requirements workbook.xlsx spreadsheet is located at:
  [new project] Capstone Support Template Documents page https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/entry/template%20documents/Needs%20and%20Requirements%20workbook.xlsx
  [continuing project] Team’s Repository, Engineering Analysis folder
Fill out based on team’s current (uninformed impression) of project
  This is first pass. Don’t worry that answers are not complete or verified by Client. You’ll be updating this often!
The Upcoming Exercise Will Help You Generate Ideas!

## Slide 57
We Use These Definitions for
IED & the Design Lab
Note – Key IED Course Materials in Capstone Support wiki.

## Slide 58: Generating Ideas for Your Needs
Spin the Wheel
Use the Topic
Write One Related Need on a Post-It
Repeat!
The Engineering Team will Play “Spin for Needs” using this link:
https://wheeldecide.com/?c1=Functionality&c2=Performance&c3=Quality&c4=Usability&c5=Accessibility&c6=Reliability&c7=Durability&c8=Availability&c9=Manufacturability&c10=Maintainability&c11=Environmental%20Impact&c12=Wild%20Card&c13=Interfaces
(be sure to copy the entire link to your browser!)
Start with the Needs you Previously Captured as part of your Meeting Prep!

## Slide 59: 15 min – Group Review of Needs & Requirements
Read notes in template document for tips
Remove/combine duplicates
Add Requirements based on the Needs
Unsure of a proper metric?
  Quick Google search to put in an educated guess
Fill in holes/gaps after looking at categories
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Requirements_Management
  Safety, Reliability, Maintainability, etc…
Take photo of whiteboard and post to Design Forum

## Slide 60: 45 min - Project Kick-Off Meeting
Meeting Agenda
  Team introductions to Client (name, major, relevant experience/skills)
  Client introduction to team
  Client describes project "in their words“
    History, ultimate and semester goals, deliverables, etc…
  Open Q&A
Document meeting minutes to Project Mgmt Forum on EDN

## Slide 61: 30 min - Prior Presentation (if applicable)
Team should review (outside of on-site meeting) the final PPT presentation given by previous engineering team
  Forums->Final Deliverables
  Repository->Reports->Final Reports
PE/CE will quickly walk-through slide deck and discuss:
  Goals
  Accomplishments / Successes
  Challenges
  Next steps
PE/CE will help to clear up confusion and answer any questions current engineering team may have

## Slide 62: 10 min - Engineering Design Process Q&A
Action Item was to watch 3 videos…
Ask me 2-3 QUESTIONS about the videos!
What are the steps in Engineering Design Process?
What is a Customer Need?
What is an Engineering Requirement?
What is the difference between a Need and a Requirement?
Notes: Day 3

## Slide 63: Engineering Design Process Q&A
What is a User Story?
  As a _____ I need to _____ so that _____
What is an Acceptance Criteria?
  Sometime defines the Minimum Viable Product
  The “least” the Client will accept as completion of the job.
Additional tools to define what will be acceptable to Client
Notes: Day 3

## Slide 64: 5 min – Wrap-up
Prep for Next Meeting
  Why
  What we are doing in the next meeting

## Slide 65: Action Items / Meeting Prep (what you might call homework, to be completed BEFORE Day 4)
Team Development / Design Process Refresher
Post Team Standards Agreement to Wiki before Day 6
Administrative Tasks
Choose Client liaison
  This person will be the focal point for emails to/from your Client. They are not the team's "spokesperson" at meetings, conference calls, on/off site meetings, etc.
Watch Intro to EDN video (5 min) for a general understanding of system usage
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/raw/training/Intro%20to%20the%20EDN.mp4
Read Meeting Minutes Wiki Page to learn how to take good meeting minutes
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Meeting_Minutes
  Post meeting minutes taken during PPT review to Project Management Forum
Follow Subversion instructions to download and install client, then checkout a copy of ONLY your project’s working folder from the Repository. Visit your PE’s office hours for assistance.
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion_Clients#section-2
Complete the Online Safety Training in Percipio by Jan 26th
  https://rpi.percipio.com/
  Rensselaer Manufacturing and Prototyping Laboratories - Safety Orientation
  Instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/raw/Course%20Documents/RMPL%20Safety%20Module%20Completion%20Instructions-Percipio%20.pdf
  Post completed safety certificate in a thread in the Project Management Forum
T/D
A
Project Technical Work
Update Needs/Reqs Workbook based on feedback and post to EDN Design Forum
P

## Slide 66: Day 4 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH on-site meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion
Playbook - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Playbook
Notes: PE Notes (Make clear for new vs. continuing on slide)
Track A or C on Day 3 should follow track A or C on Day 4
Track B, D, or E on Day 3 should follow track B or D on Day 4

## Slide 67: Engineering Design Process - Scaffolding Progression
This Design Process and terminology was learned previously in IED
Days 1-5
Days 3-5
Day 7
Day 6 – Project Statement and Objectives, Eng. Tools and Methods
Days 8-9 – Project Planning and Communication Skills

## Slide 68: 15 min – Group Review of Needs & Requirements
Read notes in template document for tips
Remove/combine duplicates
Unsure of a proper metric?
  Quick Google search to put in an educated guess
Fill in holes/gaps after looking at categories
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Requirements_Management

## Slide 69
We Use These Definitions for
IED & the Design Lab
Note – Key IED Course Materials in Capstone Support wiki.

## Slide 70: Generating Ideas for Your Needs
Spin the Wheel
Use the Topic
Write One Related Need on a Post-It
Repeat!
The Engineering Team will Play “Spin for Needs” using this link:
https://wheeldecide.com/?c1=Functionality&c2=Performance&c3=Quality&c4=Usability&c5=Accessibility&c6=Reliability&c7=Durability&c8=Availability&c9=Manufacturability&c10=Maintainability&c11=Environmental%20Impact&c12=Wild%20Card&c13=Interfaces
(be sure to copy the entire link to your browser!)
Start with the Needs you Previously Captured as part of your Meeting Prep!

## Slide 71: 45 min - Project Kick-Off Meeting
Meeting Agenda
  Team introductions to Client (name, major, relevant experience/skills)
  Client introduction to team
  Client describes project "in their words“
    History, ultimate and semester goals, deliverables, etc…
  Open Q&A

## Slide 72: 55 min - Project Work
Refine Needs and Requirements Spreadsheet
  Needs
    Ensure all known Customer Needs are documented
  Requirements:
    Associate with appropriate Customer Need(s)
    Identify Measurements and Units (quantitative)
    Ensure that Requirements are detailed and prioritized
    Identify Applicable Engineering Standards
Refine/Develop Follow-Up Questions for Client
  If Team has already had Kick-Off Meeting, what new questions have been identified as a result?
    Clearly document, review with PE then email to Client, copy your PE & CE
Background Research/Benchmarking
  Discuss/document work done to date
  Identify/document additional benchmarking needs

## Slide 73: 30 min – Meet with CE (Day 3 or 4)
Chief Engineer led discussion of:
  Performance Evaluations – aka Course grading
  Team member expectations
    Group discussions
    Project Documentation on EDN
    Action Items
  CE background and experience
  Project impressions
  Team Standards Agreement

## Slide 74: 10 min – Wrap-up
Prep for Next Meeting

## Slide 75: Action Items / Meeting Prep (to be completed BEFORE Day 5)
Team Development / Design Process Refresher
Post Team Standards Agreement to Wiki before Day 6 [1/29 or 1/26]
Administrative Tasks
Contact your PE if you are having trouble installing or using subversion
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion
Complete the Online Safety Training in Percipio by Day 6 [1/29 or 1/26]
  https://rpi.percipio.com/
  Rensselaer Manufacturing and Prototyping Laboratories - Safety Orientation
  Instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/raw/Course%20Documents/RMPL%20Safety%20Module%20Completion%20Instructions-Percipio%20.pdf
  Post completed safety certificate in a thread in the Project Management Forum
T/D
A
Project Technical Work
Evaluate your current Needs & Requirements workbook against the rubric
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/entry/Rubrics/Needs%20and%20Requirements%20rubric.docx
Each team member shall post their observations in the Needs & Requirements Design Forum Thread
P

## Slide 76: Day 5 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH on-site meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion
Playbook - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Playbook

## Slide 77: Engineering Design Process - Scaffolding Progression
This Design Process and terminology was learned previously in IED
Days 1-5
Days 3-5
Day 7
Day 6 – Project Statement and Objectives, Eng. Tools and Methods
Days 8-9 – Project Planning and Communication Skills

## Slide 78: 30 mins - Needs and Requirements
You currently have / have done:
Initial Project Description
List of Questions Based on the Project Description
Team Ideation Poster
PE Discussion on the Project Description
Draft Needs and Requirements Spreadsheet
Project Kick-off Meeting
Goal - Enhance the Needs and Requirements Spreadsheet

## Slide 79: Making Strong Needs and Requirements
Needs and Requirements are used to guide Concept Generation without suggesting or forcing a particular solution(s).
Needs and Requirements drive the future decision-making process for Concept Selection
Most Needs Will Have Many Requirements
Focus is on your Prototype rather than a “full scale” implementation
Note - Software functions are typically better captured in a different document, e.g. Use Cases and User Scenarios and NOT as part of the Needs and Requirements spreadsheet.
Software Needs Typically Define Functions and Often Do Not Have Associated Measurable Requirements

## Slide 80
We Use These Definitions for
IED & the Design Lab
Note – Key IED Course Materials in the Capstone Support wiki

## Slide 81: Examples of Making Needs Stronger for Designing a Laptop
Weakly Stated Needs | Strongly Stated Needs
The project needs a 12V battery | The device needs to operate without connection to a wall outlet.
The user needs to get a beep when a problem occurs | The user needs to get an alert when a problem occurs.
The system needs an on/off switch. | The system should minimize power usage when its not in use.
It needs to support expected loads AND the frame weight should be minimized. | It needs to support expected loads The frame weight should be minimized.
It needs to be safe. | It must meet appropriate industry safety standards.
It needs to be small | It must fit in a typical backpack.

## Slide 82: Examples of Creating Strong Requirements
Need | Requirement
The device needs to operate portably. | Operate for 24 hours. Maximum weight of 5 lbs. for entire laptop
The user needs to get an alert when a problem occurs. | Alerts must be received within 1 minute of a problem
The system should minimize power usage when its not in use | The device should can be turned back on after 12 hours In standby mode
the frame weight should be minimized. | Maximum weight of 5 lbs. for entire laptop
It needs to support expected loads | Laptop lid must support at least 2 lbs. without breaking.
It must meet appropriate industry safety standards. | Underwriter Labs – UL IEC IP rating – at least 41
It must fit in a typical backpack. | Maximum dimensions 18”x9”x2”

## Slide 83: Examples of Creating Strong Requirements
Need | Requirement
The device needs to operate portably. | Operate for 24 hours. Maximum weight of 5 lbs. for entire laptop
The user needs to get an alert when a problem occurs. | Alerts must be received within 1 minute of a problem
The system should minimize power usage when its not in use | The device should can be turned back on after 12 hours In standby mode
the frame weight should be minimized. | Maximum weight of 5 lbs. for entire laptop
It needs to support expected loads | Laptop lid must support at least 2 lbs. without breaking.
It must meet appropriate industry safety standards. | Underwriter Labs – UL IEC IP rating – at least 41
It must fit in a typical backpack. | Maximum dimensions 18”x9”x2”

## Slide 84: Design Project – Create a Vehicle
Everyone is working on the same project
Work with your team
Team Decides on Type of Vehicle
Three Rounds, Each Has:
  Design Step
  Report Out
  Questions
You’ll use the whiteboards
This exercise is time boxed!

## Slide 85: Design Project - Round 1
  Draw a Vehicle
    Create one drawing per group
    Use LEFT 1/3 of the Whiteboard
    Make picture large enough for entire team to see.
  Time Limit – 5 Minutes
  Any Questions?

## Slide 86: Questions
Did you have enough information?
Did you know what to do?
What process did you use for creating the drawing?
Did everyone have input to the drawing?
Notes: Our chance to process this out!
Some possible items: What is it used for? What kind of vehicle? How big? What kind of vehicle? To transport what (people)? How many people will it carry? What does it look like? What does it do? Does it move by itself?

## Slide 87: Design Project - Round 2
  Identify Needs for your Project
    Write the list on the Whiteboard on the MIDDLE 1/3 of the Whiteboard
  Time Limit – 5 Minutes

## Slide 88: Questions
Could you assign units to all your items?
Are the “How Much / How Many” numbers reasonable?
What process did you use for selecting the units and numbers?
Did everyone have input to the units and numbers?
Notes: Our chance to process this out!

## Slide 89: Design Project - Round 3
  Identify Requirement and Assign Metrics To Them
    Write the list on the RIGHT 1/3 of the Whiteboard
    Draw a line from each Requirement back to it’s driving Need.
    What measurement units apply to each? Write these down on the Whiteboard.
    Answer “How much / How many” for each item
  Time Limit – 5 Minutes

## Slide 90: Questions
Could you assign units to all your items?
Are the “How Much / How Many” numbers reasonable?
What process did you use for selecting the units and numbers?
Did everyone have input to the units and numbers?
Notes: Our chance to process this out!

## Slide 91: Design Project – Create a Vehicle Wrap-up
You should know the importance of Needs and Requirements
You should know how to create strong needs
You should know how to define measurable requirements
You should know how to relate the requirements to their needs
You should be better prepared to generate the
Needs and Requirements for your Capstone project

## Slide 92: 70 mins - Enhance your Project’s Needs & Requirements
Relook at Your Team’s Spreadsheet
Focus only on the Needs and Requirements Columns for Today
Evaluate Your Needs & Requirements Based on the Definitions
Make your Needs Stronger
Ensure your Requirements are Measurable
Leverage the Needs and Requirements Rubric
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/entry/Rubrics/Needs%20and%20Requirements%20rubric.docx
Commit the updated file back to your project’s repository by the end of class

## Slide 93: 10 min – Wrap-up
Day 6 activities will include creation of:
  Project Statement and Objectives (PSO)
  Engineering Tools and Methods (ETM) Worksheet
Highlight Documentation?

## Slide 94: Wrap-up
Project Statement and Objectives (PSO)
  The PSO provides an overview of your project and what the team will accomplish. It is the contract/scope the Engineering Team is agreeing to complete for the Client by the end of semester.
  It is the team’s first graded assignment!

## Slide 95: Wrap-up
Engineering Tools and Methods (ETM)
  The ETM Worksheet will help you team identify the various Engineering Tools and Methods that members will use to address project challenges
  Reviewing the Ideation Poster, specifically the “What classes and/or experience can you call on to help with this project?” and “What technical problems need to be solved to successfully complete this project?” sections should help teams identify applicable ETM.

## Slide 96: Wrap-up
Documentation?

## Slide 97: Action Items / Meeting Prep (to be completed BEFORE Day 6)
Team Development / Design Process Refresher
Post Team Standards Agreement to Wiki before Jan 26th [1/29 or 1/26]
Administrative Tasks
Read Project Documentation Wiki page in preparation for Day 6 review
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Project_Documentation
Everyone should have their repository checked out by now. See your PE NOW if you are still having difficulty.
Complete the Online Safety Training in Percipio before Friday, 01/26
  https://rpi.percipio.com/
  Rensselaer Manufacturing and Prototyping Laboratories - Safety Orientation
  Instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/raw/Course%20Documents/RMPL%20Safety%20Module%20Completion%20Instructions-Percipio%20.pdf
  Post completed safety certificate in a thread in the Project Management Forum
T/D
A
Project Technical Work
Read the Project Statement & Objectives Wiki page in preparation for Day 6 review
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Project_Statement_and_Objectives
Read the Engineering Tools and Methods Wiki page in preparation for Day 6 review
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Engineering_Tools_and_Methods_Worksheet
Update Needs & Requirements Workbook based on feedback and update file in Repository
P

## Slide 98: Day 6 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH on-site meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion
Playbook - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Playbook

## Slide 99: Engineering Design Process - Scaffolding Progression
This Design Process and terminology was learned previously in IED
Days 1-5
Days 3-5
Day 7
Day 6 – Project Statement and Objectives, Eng. Tools and Methods
Days 8-9 – Project Planning and Communication Skills
Notes: Today is Day 6. Continue building on what was learned in IED as opposed to IED refresher

## Slide 100: 10 min – Documentation & EDN Usage Q&A
You should have already watched EDN video and read Documentation Wiki page
  Intro to EDN video (5 min)
    https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/raw/training/Intro%20to%20the%20EDN.mp4
  Project Documentation page
    https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Project_Documentation
Ask me 1-2 QUESTIONS about the content!
Why do we document?
What do we document?
How will you document?
How often / when will you document?
Must we wait for things to be complete / final to document?
Where does it go?
Notes: Day 6

## Slide 101: What is Engineering Documentation?
Living record of your work so that:
  Evolution of your product/design is traceable
  Your work (experiment) is reproducible
    Sketches, ideas, discussions
    Test setup, results, failures & successes
  Your work can be understood by others and why you did it that way
  Feedback & help can be offered
  Easy to incorporate into client meeting presentations and the final design report

## Slide 102: Why Document?
Extension of your memory
  Who, What, When, Where, Why, How
  So that others can collaborate and continue the work
  Facilitates teamwork
  So that others can review/understand your work
Legal ramifications
  Contractual/legal defense
  Patent application
Efficiently and Effectively move the project forwards
Everyone (now and future) can understand the Who, What, When, Where, Why, and How of the team’s work

## Slide 103: Corporate Communication & Documentation Policies Reminder
Electronic Design Notebook - REQUIRED for all project work & effort
Webex (only) - Team Chat
WhenIsGood or When2Meet - meeting scheduling
Not Permitted
  Slack, GroupMe, or Discord
  Google Drive
  Google Docs/Sheets/Slides
  Other cloud-based tools for any use (schematics, mind maps, drawings, analysis, etc…) e.g., diagrams.net, etc.
  RPI Box, RPI Onedrive, RPI Sharepoint
Webex Teams is good for chat and live meetings, but project documentation should start on and stay in the Electronic Design Notebook (EDN) Forum or Repository.
  Simple/easy solution is to never put it on Webex (or elsewhere) to begin with.

## Slide 104: Documentation Wrap up
True or False
Information should be complete before documented?
It is necessary to document negative results?
Teammates share responsibility with PE/CE to offer technical feedback on EDN posts?

## Slide 105: 10 min - Project Statement & Objectives Q&A
Action Item was to read the wiki page…
Ask me 1-2 QUESTIONS about the content!
What is a Project Statement & Objectives (PSO)?
What is difference between the Long Term and Short Term Goals?
What is difference between an objective and a deliverable?
Where is the PSO document template located?

## Slide 106: 10 min - Engineering Tools and Methods (ETM) Q&A
Action Item was to read their wiki pages…
Ask me 1-2 QUESTIONS about the content!
What are Engineering Tools and Methods?
Give an example of a Mechanical Engineering Tool or Method
Give an example of an Electrical Engineering Tool or Method
Give an example of a Computer Systems Engineering Tool or Method
Give an example of an Industrial Engineering Tool or Method
Give an example of a Material Engineering Tool or Method

## Slide 107: 10 mins - Technical Communications
Helpful Hints for Career Success Design Lab - And Beyond!

## Slide 108: 3 Keys to Success*
Ability to Speak
Ability to Write
Quality of Your Ideas
*Prof. Patrick Winston, MIT – Director of AI Lab 1972-1997
https://www.youtube.com/watch?v=ukYi50Gfc5M

## Slide 109: Tech Memos and Reports
Differ from a Term Paper or Essay - News Article vs. Feature Story - Factual vs. Opinions
Provide Technical Information and Results - What? - Why? - How?
Reader must be able to re-produce the results

## Slide 110: Start with an Outline
What is the Key Message? Who is the Audience? Can an Uninformed Reader Understand? Avoid Information Overload (...Data Dump)
Utilize Illustrations to convey the message “A picture is worth 1000 words!” - Figures, Plots - Schematics, Diagrams - Tables, Lists - Equations
Self-Explanatory Figure Captions and Table Names Can the reader understand the diagram/table without reading the entire text?

## Slide 111: Writing Style
Clear and Concise
Short Sentences
Use Formatting for Clarity 4.0 Design Concept 4.1 Mechanical System 4.1.1 Engine 4.1.2 Powertrain 4.2 Electrical System 4.2.1 Sensors 4.2.2 Controls
Use a Scale in Figures to show Dimensions
Figure 1 – Water Column Sensor

## Slide 112: Label Plots – axes, legend (for multiple data sets)
Figure 10 GUI Screen shows sensor output

## Slide 113: Provide Supporting Information
To Support Your Hypothesis - Data - Experimental Results - Published Information
OR To Present an Alternate Perspective - Findings from the Literature
References and Citations Always Provide Attribution!
PLAGIARISM: Use of Others’ Data/Figures/Text Without Attribution is Unethical and Not Acceptable

## Slide 114: References
Include Numbered Reference List
Use MS Word Built-in Utility
All Figures and Tables must be referenced in the appropriate places in the text.
Is it a Legitimate/Reliable Reference? - Peer Reviewed Journal Articles - Technical Reports - Textbook/Handbook - Industry Website
For Web references, ensure all Reference Links are functional

## Slide 115: Reference List

## Slide 116: Refer to Figs in Text Cite Refs
Figure 7. Fathom ROV Tether [26]
Figure 7 shows the Fathom ROV Tether [26]. This cable was selected to be used to
power, communicate with, raise and lower the Sensor Pod. The cable contains four twisted pairs.

## Slide 117: Resources
- Design Lab Workshop
https://info.rpi.edu/comm-d

## Slide 118: 50 min – Creation of Project Statement and Objectives & Engineering Tools and Methods
  Templates for both documents are on the Capstone Support Wiki
    https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Templates_and_Forms
  Instructions
    https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Project_Statement_and_Objectives
    https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Engineering_Tools_and_Methods_Worksheet
  Your CE & PE are available to answer any questions and review your work
  Finish & save in ‘working\Reports\Final Report + Poster‘ folder in the Repository as Prep for next Meeting
  Files in the Repo can be revised as needed. These are drafts and your documents may later change as the engineering team learns more!

## Slide 119: Long Term vs. Short Term
Long Term:
1 – 5+ years in future
Assume there may be multiple projects / semesters / teams working AFTER yours
Assume a successful output from each team
What can the Client do / achieve 1-5+ years from now because your work was successful?
Short Term:
By the end of this semester
Things your Client wants you to achieve early this semester, by mid-semester, and at the end of the semester
Assumes your success
What can your Client do with your work immediately after the semester ends?
FYI

## Slide 120: 10 min – Wrap-up
Day 7 will focus on Concept Generation
  Now that teams have had time to begin identifying the Client Needs and corresponding Engineering Requirements associated with their projects, it is time to identify potential concepts to address them.
  The Concept Generation activity during the Day 7 on-site meeting will utilize the ideation (Post-It Note) process that we have used previously.

## Slide 121: Action Items / Meeting Prep (to be completed BEFORE Day 7)
Team Development / Design Process Refresher
Watch Concept Generation video (9 min) in preparation for Concept Generation on-site exercise
  https://mediasite.mms.rpi.edu/mediasite/Play/d78db44fd9f7424b9d8f4c72857f84371d
Administrative Tasks
This section intentionally left blank
T/D
A
Project Technical Work
Wordsmith and polish Project Statement & Objectives
    Upload to Repository - working/Reports/Design Report + Poster
Finalize Engineering Tools & Methods Worksheet
    Upload to Repository - working/Reports/Design Report + Poster
Continue Updating Needs & Requirements spreadsheet in Repository
P

## Slide 122: Day 7 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH on-site meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion
Playbook - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Playbook

## Slide 123: Engineering Design Process - Scaffolding Progression
This Design Process and terminology was learned previously in IED
Days 1-5
Days 3-5
Day 7
Day 6 – Project Statement and Objectives, Eng. Tools and Methods
Days 8-9 – Project Planning and Communication Skills
Notes: Today is Day 7. Continue building on what was learned in IED as opposed to IED refresher

## Slide 124: 10 min - Concept Generation Q&A
Action Item was to watch 1 video…
Ask me 1-2 QUESTIONS about the content!
Where do concept ideas come from?
  Example of Internal Search?
  Example of External Search?
Notes: Day 7

## Slide 125: 15 min – CE Time
Meeting will be at team table
This will take place at some point during Concept Generation exercise depending on CE’s schedule

## Slide 126: 65 Min - Concept Generation
Similar inclusive plan as previous exercises
5 min – Individually silently generate any concept to solve/address customer needs/reqs
  write separately on Post-It Notes
15 min – Place concepts on whiteboard
  Organize list by topic
  Eliminate duplicates
  Add extra ideas you think of right now or are inspired by others ideas
30 min – Group discussion
  Explain further to improve group understanding – if necessary
  Look for missing/unaddressed needs –think of concepts to address them
  Look for lone concepts – think of alternative ideas
Note - CE will jump in to talk for 15 mins of this time block

## Slide 127: 5 min – Create Forum Threads
Concept topics ARE the key discussions and work areas for the team
Create Design Forum threads for each topic
  Use these thread to post explanation, sketches, calculations, etc…
  Reply to teammate’s posts to move idea forwards and advance project
  Includes links to material as appropriate but it is helpful to explain what can be found at the link

## Slide 128: 15 min – Project Work
Work on project
Someone should take notes of meeting discussion
    NOT as Word document, simply as plain text in Forum post.
  Meeting Minutes instructions and template https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Meeting_Minutes
Post your meeting minutes AT END of the meeting to Forums –> Project Mgmt
  Others can reply to post with any corrections or additional information

## Slide 129: 10 min - Technical Memo
Team Creates (Together or Independently) A List of Topics, e.g.:
What is current state of the art? How is problem currently solved?
  Literature search on topic X and how that helps the project
  User interviews to gather additional needs and requirements
What will team members NEED to know to move forwards?
  Identifying / installing / practicing software or techniques which will be required for the project and documenting any challenges or issues
  Leverage the Team Ideation Poster - technical problems to solve!
What has already been accomplished by prior team?
  Install existing project software and identify issues and opportunities for improvement
  Verify work done by past Design Lab team(s) and identify issues and opportunities for improvement
  Conduct testing or system operation described by prior team and identify issues and opportunities for improvement
Capstone Support Wiki has instructions, template, and rubric
https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Technical_Memo

## Slide 130: 10 min - Technical Memo
If there is time during on-site meeting, team brainstorms list of topics and one person posts to Background Forum ASAP to allow collaboration
Outside of meeting, everyone review and reply with either their pick of one of those topics OR replies with a new proposed topic as their memo topic
ALL topics should directly apply to your project. It should provide useful information that will help the team better understand:
  The needs & requirement
  Possible solution concepts
  Potential technologies, tools and methods from your Problem Statement and Objectives
Your proposed topic should be SMART. This will make your writing easier and more beneficial to the team
Keep your writing focused. The memo is only 4 pages long!
PE/CE must approve your individual topic proposals

## Slide 131: 5 min – Wrap-up
During the Day 8 on-site meeting, teams will develop a project plan to guide their work for the remainder of the semester. To be prepared for this activity, team members must:
  Understand why Project Mgmt. is important
  Understand the difference between Deliverables and Tasks/Activities.
    Deliverables should be identified in the PSO.
  Come to the meeting with an initial list of tasks required to complete the project.

## Slide 132: Action Items / Meeting Prep (to be completed BEFORE Day 8)
Team Development / Design Process Refresher
Watch videos in preparation for Project Planning activity on Day 8
  Intro to Project Mgmt (7 min)
    https://www.youtube.com/watch?v=QwuwzBBThPY
  Deliverables & Activities (3 min)
    https://www.youtube.com/watch?v=L6WYJh1Ygoc
Administrative Tasks
This section intentionally left blank
T/D
A
Project Technical Work
Continue technical work
  Post progress to Design Forum threads of EDN
Post list of proposed topics for Technical Memos in Background Info forum
  Thread called “Memo topics” – notify PE/CE when posted for approval
Each team member brainstorm at least 6 individual tasks which will need to be accomplished to reach the semester objectives
  Post to a SINGLE thread in the Project Mgt. Forum called “Tasks” (first person creates thread, others reply). There should be at least 6 tasks per team member by Day 8
P

## Slide 133: Day 8 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH on-site meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion
Playbook - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Playbook

## Slide 134: Engineering Design Process - Scaffolding Progression
This Design Process and terminology was learned previously in IED
Days 1-5
Days 3-5
Day 7
Day 6 – Project Statement and Objectives, Eng. Tools and Methods
Days 8-9 – Project Planning and Communication Skills

## Slide 135: 10 min - Project Planning Q&A
Action Item was to watch 2 videos…
Ask me 1-2 QUESTIONS about the content!
What is a milestone?
What is the difference between parallel tasks and serial tasks?
What is critical path of a plan?
Notes: Use building a house as example

## Slide 136: Defining Meaningful Tasks
One idea per Post-It. Be concise!
Defined to be No More than 1 week long. Break big things into smaller pieces.
Everyone Needs at Least 1 Task / Week for the Entire Semester
What will YOU contribute to the project? Focus on YOUR potential contributions to the project. (We know these may not yet be defined!)
Focus on the technical work required
For now, leave out project management / overhead tasks, e.g., report writing, slide making, etc.
DO include documentation needed for technology transfer, e.g., user manual
Be Technical! Be SMART!
80 min - ‘Post-It Note’ Project Planning

## Slide 137: Defining Meaningful Tasks aka “SMART”
Yes, it gets harder to define tasks near the end of the semester. So instead, work backwards from the end!
There may be gaps in time – you will need to fill those in today
Do not just copy a task 3 times because it spans 3 weeks. Instead, you must break it down into 3 well defined smaller tasks.
Don’t allocate slack time at the end of the semester. Project plans do not include tasks called “Just in Case”. Instead estimate the length of tasks to factor in some risk. Not everything works the first time and many thing turn out to be more difficult than first thought.
Group things by functional subsystem rather than by name. This helps reveal possible planning gaps.
Remember your deliverables! Do you have the tasks needed to produce each of them, including things like demos?
Be Technical! Be SMART!
Project Planning Tips

## Slide 138: 20 min - ‘Post-It Note’ Project Planning
10 min – Deliverables
Write each Deliverable from Project Statement and Objectives on a Post-It and place on the board/calendar at approximate due date.
Draw a box around the note so that it stands out.
10 min – Tasks
(Individually silently) Each team member generate list of TEN tasks which must be completed to accomplish the deliverables.
Off-site Action Item was to post 6 individual tasks to EDN, so start with those. Now create at least 4 more each.
Create 1 Post-It for each task
Add your initials to post-it in case there are questions about content

## Slide 139: ‘Post-It Note’ Project Planning Exercise
10 min – Organize tasks on Whiteboard
Position tasks appropriately along week-by-week calendar
  This can be done before or after getting all items shared.
30 min – Group organization of tasks
Add missing tasks, remove duplicates
Organize by subsystem or milestone
10 min – Re-assign ownership (by color/initial)
Ensure everyone has work throughout semester
Each Team Member Should Leave meeting with their assigned Post-It’s.
Each Team Member then Enters Their Own Tasks as EDN Issues!

## Slide 140: 10 Min - Reflecting on your New Project Plan
Take a few minutes to pause and reflect on the Project Plan the Engineering Team just created.
Use the prompts on this Wiki page to guide the discussion.
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Reflecting_on_your_New_Project_Plan
Focus on Process and Results

## Slide 141: 10 min – Wrap-up
Day 9 will conclude scaffolded team meetings
The focus of Day 9’s scaffolded activities include receiving feedback on:
  The Project Plans created during and after Day 8
  The draft Client Update #1 PPT
    This PPT will be used both for your first Client Update Meeting as well as (with some minor changes) the Board of Directors (BDR) Review

## Slide 142: Wrap-up
Day 9 also includes 60 minutes of time for team-directed work.
  Efficient team-directed meetings require an Agenda.
  The Agenda should be SMART - Specific, Measurable, Actionable, Relevant, and Time-Oriented
  Agendas should be posted to your white board before starting the meeting
    Pro Forma Agenda posted on Capstone Support: https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Pro_Forma_Meeting_Agenda

## Slide 143: Action Items/ Meeting Prep (to be completed BEFORE Day 9)
Team Development / Design Process Refresher
Read Risks Associated with Project Plans Wiki page and revise team plan in EDN Gantt chart as necessary
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Risks_Associated_with_Project_Plans
Administrative Tasks
Create draft of Client Meeting #1 PPT and upload to the Repo BY START OF Day 9
  Template - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Templates_and_Forms
  Repository location – working/Reports/Client Meetings
Create agenda for 60 mins of Day 9, team’s plan should NOT be just working on your Client Meeting slides!
T/D
A
Project Technical Work
Add deliverables from Project Statement & Objectives to EDN Gantt Chart as Versions
  Watch video with instructions (4 min) - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/raw/training/Creating%20Versions%20from%20your%20Statement%20of%20Work.mp4
  Prefix with current semester name/year, e.g. “F23-” to avoid duplication of common deliverable names across semesters.
Add tasks identified on sticky notes into EDN as Issues and associate them with the appropriate version and assignee (owner)
Technical Memo due on 02/08 (Sections 1/2) / 02/06 (Sections 3/4)
  Memo Information: https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Technical_Memo
  Submit your memo by Uploading to the Background Information folder in team’s Repository
    Include your RCSID and topic in filename, e.g “deboeb Threaded Fasteners.docx”
P

## Slide 144: Day 9 Agenda
  You are STRONGLY ENCOURAGED to download newest version of Playbook prior to EACH on-site meeting.
Repository instructions - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Subversion
Playbook - https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/wiki/Capstone_Playbook

## Slide 145: Engineering Design Process - Scaffolding Progression
This Design Process and terminology was learned previously in IED
Days 1-5
Days 3-5
Day 7
Day 6 – Project Statement and Objectives, Eng. Tools and Methods
Days 8-9 – Project Planning and Communication Skills

## Slide 146: 60 min – Follow Team created Agenda
Designate team member to facilitate this meeting
Designate team member to take and post minutes to EDN
  This should be done for EVERY on-site and off-site meeting.
  Rotate responsibility. To be equitable, ALL team members should have a turn!
Notes: Day 9

## Slide 147: 15 min – PE Review Project Plan
Many short individual tasks? Few large group tasks?
Adequate time for:
  Manufacturing?
  Purchasing?
  Testing?
  Iterative development? Second round of any tasks?
Equal division of labor across all team members?
Ability to do some work in parallel rather than series?
  Design test plan BEFORE fabrication is complete
  Create dummy data NOW to test software performance or analysis approach

## Slide 148: 30 min – PE Review of Client Meeting PPT
Checklist
Are slides numbered?
Are figures labeled?
Have Team members names, PE/CE names & depts, Client name and logo been updated from blank template?
Does agenda match actual contents of PPT?
Do the contents match the rubric and Project Statement & Objectives content?
  Background & Customer Needs
  Technology Assessment
  Engineering Requirements
  Concept Generation

## Slide 149: 5 Min – Wrap-up
Scaffolded Employee Onboarding and Project Scoping activities have ended!
Primary purpose of the remaining on-site meetings is team review and assessment of work already completed, especially with your PE and/or CE.
These 4 hours per week of on-site meeting time may be the only available time for FULL Engineering team to meet. It is therefore recommended to use this time for group discussions, group work, planning, updating Needs and Requirements, making decisions, etc. IF all that is complete / up to date, use the time for individual work.
Use EDN and Repository to document all work moving forwards

## Slide 150: Action Items / Meeting Prep (to be completed BEFORE Day 10)
Team Development / Design Process Refresher
This section intentionally left blank
Administrative Tasks
Address any feedback received on Client Meeting PPT
Client liaison should email PPT to Client no later than 24 hours prior to call. This person will be the focal point for emails to/from your Client. They are not the team's "spokesperson" at meetings, conference calls, etc.
Prep for upcoming client meeting, e.g., identify speakers for each slide, prepare your notes, etc.
T/D
A
Project Technical Work
Continue technical work
Post progress to Design Forum thread(s)
Team members should now be creating and updating their individual project tasks
Wordsmith and polish Engineering Standards Worksheet
    Upload to Repository - working/Reports/Design Report + Poster
P

## Slide 151: All Employee Meetings

## Slide 152: 5 min – BDR Q&A
Action Item was to watch review 1 Wiki page…
Ask me 1-2 QUESTIONS about the content!
What does BDR stand for?
Who is audience for BDR?
Approx. how many PPT slides should team prepare?
BDR Introduction
Notes: Day 9

## Slide 153: Engineering Design Process
Team is creating a poster to communicate
Overall project (Needs & Requirements)
Progress made (Concepts, System Architecture)
Future steps (Design, Integration, & Test Plan)
This Design Process and terminology is taught in IED at RPI
POSTER introduction
Notes: Day 9

## Slide 154: 95 min – Poster Creation
Download and Open Poster.pptx from Repository
  https://designlab.eng.rpi.edu/edn/projects/capstone-support-dev/repository/112/entry/template%20documents/Poster.pptx
10 mins – Divide into 3 groups, and work on initial slides. Content can be pulled from Project Statement & Objectives.
  Purpose
  Past Work and/or Project History
  Semester Objectives/Requirements
40 mins – As a full team discuss Technical Approach, Results and Accomplishments to Date
30 mins – Move on to Next Steps and Plan
15 mins – Begin assembly of content onto single slide (pg 8)

## Slide 155: Revision History
Version | Date | Name | Reason for Changes
2.0 | 1.3.24 | MA | First edit of new year! Adding in Day 5=N&R and replacing with new Slido based icebreaker
2.1 | 1.4.24 | BD | Revised EDP slide to “Universal”, added wrap-ups @ end of each day to discuss next day’s activity, changed from “Employee Onboarding” to “Project Scoping” after Day 2.
2.3 | 1.4.24 | BD | Updates to Action Items and Wrap-up slides for first week.
2.4 | 1.5.24 | AP | Removed “believe in” from core values, removed last references to Employee Feedback Heading added to table on p82+83
2.5 | 1.5.24 | BD | Changed from “scaffolded sessions” to “scaffolded meetings”, rearranged Action Items/Meeting Prep slides to put Project work @ bottom
2.6 | 1.5.24 | BD/AP/MA/JK | Minor updates to/cleanup of Action Items/Meeting Prep slides
2.7 | 1.5.24 | BD/MA | Updated speaker notes, identified “you are here” on Design Process slides
2.8 | 1.5.24 | AP | Updated Agenda graphics for all days
2.8675309 | 1.6.23 | AP | Updated Action Items for between on-site meetings Some formatting of slides to improve readability and consistency Update Team Standard and Safety Training for Day 6 – 1/29 or 1/26
2.9 | 1.8.23 | AP | Updated times and link for Team Building activity Fixed typos on Action Item lists and timing of activities

## Slide 156: Revision History - continued
Version | Date | Name | Reason for Changes