## DAY 1
F24
| 1 |  |  | Department activity
Team activity
category
| Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 5 | Welcome! Find your team pod | A
| 10:05 | 12:05 | 5 | Logistics | A | P | 15
| 10:10 | 12:10 | 15 | Course Introduction & Expectations part 1 | A | T | 35
| 10:25 | 12:25 | 25 | Ice Breaker Activity | T | A | 40
| 10:50 | 12:50 |  |  | A
|  |  | 10 | CE Introductions | T
| 10:50 | 12:50 | 15 | PE Introductions | P
|  |  |  | Project Description Review ? | P
|  |  | 10? | Team Standard Agreement
| 11:05 | 13:05 | 5 | Team Building Activity Intro | A
| 11:10 | 13:10 | 10 | Wrap Up | A
|  | Total Duration (min) | 90
CE & PE will jump between Teams
IGNORE all colors, IGNORE all times
yellow highlights are open questions/discussion
| 1 |  |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
Webex Meetings
MC
PE |  |  |  | start in PE Team Space | category
| Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 5 | Welcome! Find your "seat" (join PE Webex Team Space) | A
| 10:05 | 12:05 | 5 | Logistics | A
| 10:10 | 12:10 | 15 | Course Introduction & Expectations part 1 | A
| 10:25 | 12:25 | 5 | Ice Breaker Instructions | T
shift to Project Team Space
| 10:30 | 12:30 | 5 | Team Member Intros | T
| 10:35 | 12:35 | 20 | Ice Breaker Activity | T
[6 empty] | P | 45
|  |  |  | shift to PE Team space |  | T | 30
| 10:55 | 12:55 | 5 | Introduction to Question Generation | P | A | 35
shift to Project Team Space
| 11:00 | 13:00 | 40 | CE & PE Introductions Project Description Review Generate Project Questions | P
shift to PE Team space
| 11:40 | 13:40 | 5 | Ticket Out Intro | A
| 11:45 | 13:45 | 5 | Wrap Up | A
|  | Total Duration (min) | 110
Post-Class Ticket Out (complete outside of class)
CE & PE will jump between Project Team Spaces
HOW to add time
PE NOTES | [7 empty] | 10:00 | 10
Every sheet has a hidden row with summation of time, in case we want to shift things and double check math | [7 empty] | 10:10
I gave up on specifically calling out location shifts after class 4. Should have the flow of things by then.
Snapshot from S22
| 1 |  |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
Webex Meetings
MC
PE |  |  |  | start in PE Team Space | category
| Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 10 | Welcome! Find your "seat" (join PE Webex Team Space) | T
| 10:10 | 12:10 | 10 | Logistics | A
| 10:20 | 12:20 | 15 | Course Introduction & Expectations part 1 | A
| 10:35 | 12:35 | 5 | Team Ideation Introduction | T
[6 empty] | P | 50
|  |  |  | shift to Project Team Space |  | T | 15
| 10:40 | 12:40 | 30 | Team Ideation Exercise | P | A | 45
| 11:10 | 13:10 | 20 | Ideation Summary Table / Technical Task List | P
shift to PE Team space
| 11:30 | 13:30 | 10 | Full Class - Questions about IED and Capstone readiness | A
| 11:40 | 13:40 | 5 | Ticket Out Intro | A
| 11:45 | 13:45 | 5 | Wrap Up | A
|  | Total Duration (min) | 110
Post-Class Ticket Out (complete outside of class)
CE will jump into Project Team Space for their 5 minute personal introduction
Snapshot from S21 (no changes after early Feb)
| 1 |  |  | Webex Teams - Project space (by team)
Webex Teams - PE space (multiple teams w/ common PE)
Webex Meetings
start in PE Team Space
| Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 10 | Welcome! Find your "seat" (join PE Webex Team Space)
| 10:20 | 12:30 | 20 | Course Introduction, Logistics, & Expectations part 1
| 10:30 | 12:40 | 10 | Orientation Packet
| 10:50 | 1:00 | 5 | Team Ideation Presentation Introduction
shift to Project Team Space
| 10:55 | 1:05 | 30 | Team Ideation Presentation Exercise
| 11:25 | 1:35 | 20 | Ideation Summary Table / Technical Task List
shift to PE Team space
| 11:45 | 1:55 | 10 | Full Class - Questions about IED and Capstone readiness
| 11:55 | 2:05 | 5 | Ticket Out Intro
|  | Total Duration (min) | 110
Post-class Ticket Out (complete outside of class)
CE will jump into Project Team Space for their 5 minute personal introduction

## DAY 2
F24
| 2 |  |  | Department activity
Team activity
category
| Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 10 | Design Lab Expectations Q&A |  | A
| 10:10 | 12:10 | 35 | Project Description Review |  | P | P | 80
| 10:45 | 12:45 | 15 | Team Skill Assessment (w ideation process intro) |  | P | T | 0
| 11:00 | 13:00 |  | PSO v1 Introduction |  | P | A | 30
| 11:00 | 13:00 | 30 | A/B - Generate Questions for Client |  | P
| 11:30 | 13:30 |  | B/A - Project Needs |  | P
| 11:30 | 13:30 |  |  |  | P
| 11:30 | 13:30 | 10 | Company Communication & Document Policy |  | A
| 11:40 | 13:40 | 5 |  |  | A
| 11:45 | 13:45 | 5 | Wrap Up |  | A
|  | Total Duration (min) | 110
CE & PE will jump between Teams
| 2 |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
Webex Meetings
MC
PE/CE |  |  |  | start in PE Team Space | [8 empty] | category
| Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 15 | Capstone Introduction and Expectations Q&A | [8 empty] | A
| 10:15 | 12:15 | 5 | Team Ideation Introduction | [8 empty] | A
shift to Project Team Space
| 10:20 | 12:20 | 30 | Team Ideation Exercise | [8 empty] | P
| 10:50 | 12:50 | 20 | Ideation Summary Table Technical Task List | [8 empty] | P
|  |  |  | Classify Questions | [9 empty] | P | 70
| 11:10 | 13:10 | 20 | Assign Questions | [8 empty] | P | T | 0
|  |  |  | PE / CE Review of Questions | [9 empty] | A | 40
shift to PE Team space
| 11:30 | 13:30 | 15 | Engineering Documentation | [8 empty] | A
| 11:45 | 13:45 | 5 | Wrap Up | [8 empty] | A
|  | Total Duration (min) | 55 |  |  |  | 35 |  |  |  | 35
Post-Class Ticket Out (complete outside of class)
Snapshot from S22
| 2 |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
Webex Meetings
MC
PE/CE |  |  |  | start in PE Team Space | [8 empty] | category
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 15 | Capstone Introduction and Expectations Q&A | [8 empty] | A
shift to Project Team Space
| Track A |  |  |  | Track B |  |  |  | Track C
| 10:15 | 12:15 | 20 | Generate Project Questions | 10:15 | 12:15 | 20 | Generate Project Questions | 10:15 | 12:15 | 30 | In Depth Project Introduction (PE) | P | P | 35
| 10:35 | 12:35 | 5 | Classify Questions | 10:35 | 12:35 | 15 | Meet with Chief Engineer | 10:45 | 12:45 | 15 | Generate Project Questions | P | T | 35
| 10:40 | 12:40 | 10 | Assign Questions | 10:50 | 12:50 | 20 | Meet with Project Engineer | 11:00 | 13:00 | 5 | Classify Questions | P | A | 40
| 10:50 | 12:50 | 15 | Meet with Chief Engineer | 11:10 | 13:10 | 5 | Classify Questions | 11:05 | 13:05 | 5 | Assign Questions | T
| 11:05 | 13:05 | 20 | Meet with Project Engineer | 11:15 | 13:15 | 10 | Assign Questions | 11:10 | 13:10 | 15 | Meet with Chief Engineer | T
shift to PE Team space
| 11:25 | 13:25 | 20 | Engineering Documentation | [8 empty] | A
| 11:45 | 13:45 | 5 | Wrap Up | [8 empty] | A
|  | Total Duration (min) | 110 |  |  |  | 110 |  |  |  | 110
Post-Class Ticket Out (complete outside of class)
Teams will be assigned to a track
You will be notified which track to follow
Snapshot from S21 (no changes after early Feb)
| 2 |  | Webex Teams - Project space (by team)
Webex Teams - PE space (multiple teams w/ common PE)
Webex Meetings
start in PE Team Space
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| 10:10 | 12:20 | 30 | Capstone Introduction and Expectations part 2
shift to Project Team Space
| Track A |  |  |  | Track B |  |  |  | Track C
| 10:40 | 12:50 | 20 | Generate Project Questions | 10:40 | 12:50 | 20 | Generate Project Questions | 10:40 | 12:50 | 30 | In Depth Project Introduction (PE)
| 11:00 | 1:10 | 5 | Classify Questions | 11:00 | 1:10 | 20 | Project Engineer Meeting | 11:10 | 1:20 | 15 | Generate Project Questions
| 11:05 | 1:15 | 10 | Assign Questions | 11:20 | 1:30 | 5 | Classify Questions | 11:25 | 1:35 | 5 | Classify Questions
| 11:15 | 1:25 | 20 | Project Engineer Meeting | 11:25 | 1:35 | 10 | Assign Questions | 11:30 | 1:40 | 5 | Assign Questions
shift to PE Team space
| 11:35 | 1:45 | 15 | Engineering Documentation
| 11:50 | 2:00 | 10 | Full Class Wrap Up
|  | Total Duration (min) | 110 |  |  |  | 110 |  |  |  | 110

## DAY 3
F24
| 3 |  |  | Department activity
Team activity
category
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 5 | Week 2 Schedule Intro | [20 empty] | A
| 10:05 | 12:05 | 10 | ENGINEERING DESIGN PROCESS Q&A | [20 empty] | T
[26 empty] | P | 45
| Track A |  |  |  | Track C - Continuing project |  |  |  | Track E | [16 empty] | T | 55
| 10:15 | 12:15 | 45 | Project Kickoff Meeting | 10:15 | 12:15 | 30 | Meet with Chief Engineer | 10:15 | 12:15 | 30 | Meet with Chief Engineer | [12 empty] | T | A | 10
| 11:00 | 13:00 | 45 | Initial Client Needs & Reqs | 10:45 | 12:45 | 30 | Update Needs & Reqs | 10:45 | 12:45 | 45 | Initial Client Needs & Reqs | [12 empty] | P
[5 empty] | 11:15 | 13:15 | 30 | Review previous team's Final PPT | 11:30 | 13:30 | 15 | Group review of Needs & Reqs
| Track B |  |  |  | Track D - Continuing project |  |  |  | Track F
| 10:15 | 12:15 | 45 | Initial Client Needs & Reqs | 10:15 | 12:15 | 30 | Review previous team's Final PPT | 10:15 | 12:15 | 45 | Initial Client Needs & Reqs
| 11:00 | 13:00 | 45 | Project Kickoff Meeting | 10:45 | 12:45 | 30 | Update Needs & Reqs | 10:45 | 12:45 | 15 | Group review of Needs & Reqs
[5 empty] | 11:15 | 13:15 | 30 | Meet with Chief Engineer | 11:30 | 13:30 | 30 | Meet with Chief Engineer
| 11:45 | 13:45 | 5 | Wrap Up | [20 empty] | A
|  | Total Duration (min) | 200 |  |  |  | #REF! |  |  |  | 110 |  |  |  | 110 |  |  |  | 110 |  |  |  | 105
Teams will be assigned to a track
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor
| 3 |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
Webex Meetings
MC
PE/CE |  |  |  | start in PE Team Space | [20 empty] | category
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 5 | Week 2 Schedule Intro | [20 empty] | A
| 10:05 | 12:05 | 10 | ENGINEERING DESIGN PROCESS Q&A | [20 empty] | T
|  |  | shift to Webex meeting |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space
| Track A |  |  |  | Track B |  |  |  | Track C |  |  |  | Track D |  |  |  | Track E |  |  |  | Track E |  |  |  |  | P | 45
| 10:15 | 12:15 | 45 | Sponsor Kickoff | 10:15 | 12:15 | 30 | Meet with Chief Engineer | 10:15 | 12:15 | 30 | Review previous team's Final Presentation | 10:15 | 12:15 | 45 | Initial Customer Needs & Reqs | 10:15 | 12:15 | 30 | Meet with Chief Engineer | 10:15 | 12:15 | 30 | Meet with Chief Engineer | T | T | 55
| 11:00 | 13:00 | 45 | Initial Customer Needs & Reqs | 10:45 | 12:45 | 45 | Initial Customer Needs & Reqs | 10:45 | 12:45 | 15 | Update Needs & Reqs | 11:00 | 13:00 | 15 | Group review of Needs & Reqs | 10:45 | 12:45 | 45 | Review previous team's Final Presentation | 10:45 | 12:45 | 45 | Review previous team's Final Presentation | P | A | 10
[5 empty] | 11:30 | 13:30 | 15 | Group review of Needs & Reqs | 11:00 | 13:00 | 45 | Sponsor Kickoff | 11:15 | 13:15 | 30 | Meet with Chief Engineer | 11:30 | 13:30 | 15 | Update Needs & Reqs | 11:30 | 13:30 | 15 | Update Needs & Reqs
shift to PE Team space
| 11:45 | 13:45 | 5 | Wrap Up | [20 empty] | A
|  | Total Duration (min) | 110 |  |  |  | 110 |  |  |  | 110 |  |  |  | 110 |  |  |  | 110 |  |  |  | 105 |  | A
Post-Class Ticket Out (complete outside of class)
Teams will be assigned to a track
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor
Snapshot from S21 (no changes after early Feb)
| 3 |  | Webex Teams - Project space (by team)
Webex Teams - PE space (multiple teams w/ common PE)
Webex Meetings
start in PE Team Space
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| 10:10 | 12:20 | 5 | Week 2 Schedule Intro
| 10:15 | 12:25 | 15 | Review of ENGINEERING DESIGN PROCESS
|  |  | shift to Webex meeting |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space
| Track A |  |  |  | Track B |  |  |  | Track C |  |  |  | Track D |  |  |  | Track E (use B or D on Day 4) |  |  |  | Track E (use B or D on Day 4)
| 10:30 | 12:40 | 45 | Sponsor Kickoff | 10:30 | 12:40 | 30 | CE meeting with team | 10:30 | 12:40 | 30 | Review previous team's Final Presentation | 10:30 | 12:40 | 45 | Initial Customer Needs & Reqs | 10:30 | 12:40 | 30 | CE meeting with team | 10:30 | 12:40 | 30 | CE meeting with team
| 11:15 | 1:25 | 45 | Initial Customer Needs & Reqs | 11:00 | 1:10 | 45 | Initial Customer Needs & Reqs | 11:00 | 1:10 | 15 | Update Needs & Reqs | 11:15 | 1:25 | 15 | Group review of Needs & Reqs | 11:00 | 1:10 | 45 | Review previous team's Final Presentation | 11:00 | 1:10 | 45 | Review previous team's Final Presentation
[5 empty] | 11:45 | 1:55 | 15 | Group review of Needs & Reqs | 11:15 | 1:25 | 45 | Sponsor Kickoff | 11:30 | 1:40 | 30 | CE meeting with team | 11:45 | 1:55 | 15 | Update Needs & Reqs | 11:45 | 1:55 | 15 | Update Needs & Reqs
|  | Total Duration (min) | 110 |  |  |  | 110 |  |  |  | 110 |  |  |  | 110 |  |  |  | 110 |  |  |  | 110
Post-class Ticket Out (complete outside of class)
Teams will be assigned to a track
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor

## DAY 4
F24
| 4 |  |  | Department activity
Team activity
category
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| Track A |  |  |  | Track B
| 10:00 | 12:00 | 30 | Meet with Chief Engineer | 10:00 | 12:00 | 45 | Project Kickoff Meeting | [8 empty] | T | P | 70
| 10:30 | 12:30 | 15 | Group review of Needs & Reqs | [12 empty] | P | T | 30
| 10:45 | 12:45 | 55 | Project Work | 10:45 | 12:45 | 55 | Project Work | [8 empty] | P | A | 10
| Track C |  |  |  | Track D
| 10:00 | 12:00 | 15 | Group review of Needs & Reqs | 10:00 | 12:00 | 55 | Project Work
| 10:15 | 12:15 | 55 | Project Work
| 11:10 | 13:10 | 30 | Meet with Chief Engineer | 10:55 | 12:55 | 45 | Project Kickoff Meeting
| 11:40 | 13:40 | 10 | Wrap Up | [12 empty] | A
|  | Total Duration (min) | 210 |  |  |  | 110 |  |  |  | 110 |  |  |  | 110
Teams will be assigned to a track which MAY BE A DIFFERENT letter than Day 3
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor
| 4 |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
MC |  |  | Webex Meetings
PE/CE
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | category
|  |  | start in Project Team Space |  |  |  | start in Webex meeting |  |  |  | start in Project Team Space |  |  |  | start in Project Team Space
| Track A |  |  |  | Track B |  |  |  | Track C |  |  |  | Track D
| 10:00 | 12:00 | 30 | Meet with Chief Engineer | 10:00 | 12:00 | 45 | Sponsor Kickoff | 10:00 | 12:00 | 15 | Group review of Needs & Reqs | 10:00 | 12:00 | 55 | Project Work | T
| 10:30 | 12:30 | 15 | Group review of Needs & Reqs |  |  |  |  | 10:15 | 12:15 | 55 | Project Work |  |  |  |  | P
| 10:45 | 12:45 | 55 | Project Work | 10:45 | 12:45 | 55 | Project Work | 11:10 | 13:10 | 30 | Meet with Chief Engineer | 10:55 | 12:55 | 45 | Sponsor Kickoff | P | P | 70
[18 empty] | T | 30
|  |  | shift to PE Team space | [14 empty] | A | 10
| 11:40 | 13:40 | 10 | Wrap Up | [12 empty] | A
|  | Total Duration (min) | 110 |  |  |  | 110 |  |  |  | 110 |  |  |  | 110
Post-Class Ticket Out (complete outside of class)
Teams will be assigned to a track which MAY BE A DIFFERENT letter than Day 3
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor
Snapshot from S21 (no changes after early Feb)
| 4 |  | Webex Teams - Project space (by team)
Webex Teams - PE space (multiple teams w/ common PE)
Webex Meetings
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
|  |  | start in Project Team Space |  |  |  | start in Webex meeting |  |  |  | start in Project Team Space |  |  |  | start in Project Team Space
| Track A |  |  |  | Track B |  |  |  | Track C |  |  |  | Track D
| 10:10 | 12:20 | 30 | CE meeting with team | 10:10 | 12:20 | 45 | Sponsor Kickoff | 10:10 | 12:20 | 15 | Group review of Needs & Reqs | 10:10 | 12:20 | 55 | Project Work
| 10:40 | 12:50 | 15 | Group review of Needs & Reqs |  |  |  |  | 10:25 | 12:35 | 55 | Project Work | 11:05 | 1:15 | 45 | Sponsor Kickoff
| 10:55 | 1:05 | 55 | Project Work | 10:55 | 1:05 | 55 | Project Work | 11:20 | 1:30 | 30 | CE meeting with team
|  | Total Duration (min) | 100 |  |  |  | 100 |  |  |  | 100 |  |  |  | 100
Post-class Ticket Out (complete outside of class)
Teams will be assigned to a track which MAY BE A DIFFERENT letter than Day 3
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor

## DAY 5
F24
| 5 |  |  | Department activity
Team activity
category
| Start time |  | Duration (min) | Activity
| 250:00 | 300:00 | 30 | Concept Generation Ideation | A | P | 70
| 250:30 | 300:30 | 70 | Research on existing technology | P | T | 0
| 251:40 | 301:40 | 10 | Wrap Up | A | A | 40
|  | Total Duration (min) | 80
CE & PE will jump between Teams
NEEDS & REQ Day added S24

## DAY 6
F24
| 6 |  |  | Department activity
Team activity
category
| Start time |  | Duration (min) | Activity
| 250:00 | 300:00 | 10 | Documentation and EDN Usage |  | A
| 250:10 | 300:10 | 10 | Engineering Tools & Methods Q&A |  | A
| 250:20 | 300:20 | 10 | Engineering Tools & Methods |  | A
| 250:30 | 300:30 | 10 | Creation of ETM |  | A
| 250:40 | 300:40 | 10 | Concept Generation |  | P | P | 60
| 250:50 | 300:50 | 50 | Research on existing technology |  | P | T | 0
| 251:40 | 301:40 | 10 | Wrap Up |  | A | A | 50
|  | Total Duration (min) | 100
| 5 |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
MC |  |  | Webex Meetings
category
| Start time |  | Duration (min) | Activity
| 250:00 | 300:00 | 15 | Documentation and EDN Usage | A
| 250:15 | 300:15 | 10 | Statement of Work Q&A | A
PE | 250:25 | 300:25 | 10 | Engineering Tools & Methods | P
CE | 250:35 | 300:35 | 65 | Statement of Work Exercise | P
| 251:40 | 301:40 | 10 | Wrap Up | A | P | 75
|  | Total Duration (min) | 95 |  |  | P | 0
[6 empty] | T | 0
|  |  | Post-Class Ticket Out (complete outside of class) |  |  | A | 35
Snapshot from S21 (no changes after early Feb)
| 5 |  | Webex Teams - Project space (by team)
Webex Teams - PE space (multiple teams w/ common PE)
Webex Meetings
| Start time |  | Duration (min) | Activity
| 10:10 | 12:20 | 30 | Documentation and EDN Usage
| 10:40 | 12:50 | 10 | Statement of Work Intro
| 10:50 | 1:00 | 10 | Eng Tools & Methods
| 11:00 | 1:10 | 60 | Statement of Work Exercise
|  | Total Duration (min) | 110
Post-class Ticket Out (complete outside of class)

## DAY 7
F24
| 7 |  |  | Department activity
Team activity
category
| Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 10 |  |  | T
| 10:10 | 12:10 | 65 | Concept Selection |  | P
| 11:15 | 13:15 | 5 | Create Forum Threads |  | P | P | 95
| 11:20 | 13:20 | 15 | Project Technical Work |  | P | T | 10
| 11:35 | 13:35 | 10 | Technical Memo Introduction |  | P | A | 5
| 11:45 | 13:45 | 5 | Wrap Up |  | A
|  | Total Duration (min) | 110
15 min CE meeting somewhere within Ideation time with Team
| 6 |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
MC |  |  | Webex Meetings
PE/CE |  |  |  |  | category
| Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 10 | Concept Generation Q&A | T
| 10:10 | 12:10 | 65 | Concept Generation Ideation | P
| 11:15 | 13:15 | 5 | Create Forum Threads | P
| 11:20 | 13:20 | 15 | Project Technical Work | P
| 11:35 | 13:35 | 10 | Background Memo Introduction | P | P | 95
| 11:45 | 13:45 | 5 | Wrap Up | A | T | 10
|  | Total Duration (min) | 110 |  | P | A | 5
[6 empty] | A | 5
15 min CE meeting somewhere within Ideation time in Team Space
Snapshot from S21 (no changes after early Feb)
| 6 |  | Webex Teams - Project space (by team)
Webex Teams - PE space (multiple teams w/ common PE)
Webex Meetings
| Start time |  | Duration (min) | Activity
| 10:10 | 12:20 | 10 | Concept Intro
| 10:20 | 12:30 | 65 | Concept Generation Ideation
| 11:25 | 1:35 | 10 | Create Forum Threads
| 11:35 | 1:45 | 15 | Project Technical Work
| 11:50 | 2:00 | 10 | Risk Analysis Memo Introduction
|  | Total Duration (min) | 110
15 min CE meeting somewhere within Ideation time in CE personal Webex Room

## DAY 8
F24
| 8 |  |  | Department activity
Team activity
category
| Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 10 | Project Planning Q&A |  | T
| 10:10 | 12:10 | 80 | Sticky Note Project Planning Exercise |  | P
| 11:30 | 13:30 | 10 | Reflect on Project Plan
| 11:40 | 13:40 | 10 | Wrap Up |  | A | P | 80
|  | Total Duration (min) | 110 |  |  |  | T | 10
[7 empty] | A | 10
| 7 |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
MC |  |  | Webex Meetings
PE/CE |  |  |  |  | category
| Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 10 | Project Planning Q&A | T
| 10:10 | 12:10 | 90 | Sticky Note Gantt Chart Exercise | P
| 11:40 | 13:40 | 10 | Wrap Up | A
|  | Total Duration (min) | 110 |  | T
[6 empty] | P | 90
[6 empty] | T | 10
[6 empty] | A | 10
Snapshot from S21 (no changes after early Feb)
| 7 |  | Webex Teams - Project space (by team)
Webex Teams - PE space (multiple teams w/ common PE)
Webex Meetings
| Start time |  | Duration (min) | Activity
| 10:10 | 12:20 | 15 | Intro to Project Planning
| 10:25 | 12:35 | 95 | Sticky Note Gantt Chart Exercise
|  | Total Duration (min) | 110

## DAY 9
F24
| 9 |  |  | Department activity
Team activity
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | category
| Track A |  |  |  | Track B
| 10:00 | 12:00 | 60 | Follow team created Class 9 Agenda | 10:00 | 12:00 | 30 | Client Meeting #2 | P | P | 90
[5 empty] | 10:30 | 12:30 | 15 | PE review of Client Meeting #1 PPT |  | T | 15
| 11:00 | 13:00 | 30 | PE review of Client Meeting #1 PPT | 10:45 | 12:45 | 60 | PE review of Project Plan | P | A | 5
|  |  |  | PE review of Project Plan |  |  |  | Follow team created Class 9 Agenda
| 11:30 | 13:30 | 15 | Client Meeting #2 |  |  |  |  | T
Risk Management
| 11:45 | 13:45 | 5 | Wrap Up |  |  |  |  | A
|  | Total Duration (min) | 110 |  |  |  | #REF!
Teams will be assigned to a track
You will be notified which track to follow
| 8 |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
Webex Meetings
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | category
| Track A |  |  |  | Track B
| 10:00 | 12:00 | 45 | Follow team created Class 8 Agenda | 10:00 | 12:00 | 30 | PE review of Initial Status Update PPT | P
[5 empty] | 10:30 | 12:30 | 15 | PE review of Project Plan
| 10:45 | 12:45 | 30 | PE review of Initial Status Update PPT | 10:45 | 12:45 | 45 | Follow team created Class 8 Agenda | P
| 11:15 | 13:15 | 15 | PE review of Project Plan |  |  |  |  | T | P | 90
[10 empty] | T | 15
| 11:30 | 13:30 | 15 | Follow team created Class 8 Agenda & continue Project Technical Work |  |  |  |  | P | A | 5
| 11:45 | 13:45 | 5 | Wrap Up |  |  |  |  | A
|  | Total Duration (min) | 110 |  |  |  | 110
Teams will be assigned to a track
You will be notified which track to follow
Snapshot from S21 (no changes after early Feb)
| 8 |  | Webex Teams - Project space (by team)
Webex Teams - PE space (multiple teams w/ common PE)
Webex Meetings
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| Track A |  |  |  | Track B
| 10:10 | 12:20 | 30 | Follow team created Class 8 Agenda | 10:10 | 12:20 | 30 | PE review of Initial Status Update PPT
| 10:40 | 12:50 | 30 | PE review of Initial Status Update PPT | 10:40 | 12:50 | 30 | Follow team created Class 8 Agenda
| 11:10 | 1:20 | 50 | Follow team created Class 8 Agenda & continue Project Technical Work
|  | Total Duration (min) | 110 |  |  |  | 110
Teams will be assigned to a track
You will be notified which track to follow

## DAY 10
F24
| 10 |  |  | Department activity
Team activity
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | category
| Track A |  |  |  | Track B
| 10:00 | 12:00 | 60 | Follow team created Class 9 Agenda | 10:00 | 12:00 | 30 | PE review of Client Meeting #1 PPT | P | P | 90
[5 empty] | 10:30 | 12:30 | 15 | PE review of Project Plan |  | T | 15
| 11:00 | 13:00 | 30 | PE review of Client Meeting #1 PPT | 10:45 | 12:45 | 60 | Follow team created Class 9 Agenda | P | A | 5
| 11:30 | 13:30 | 15 | PE review of Project Plan |  |  |  |  | T
| 11:45 | 13:45 | 5 | Wrap Up |  |  |  |  | A
|  | Total Duration (min) | 110 |  |  |  | #REF!
Teams will be assigned to a track
You will be notified which track to follow
| 8 |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
Webex Meetings
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | category
| Track A |  |  |  | Track B
| 10:00 | 12:00 | 45 | Follow team created Class 8 Agenda | 10:00 | 12:00 | 30 | PE review of Initial Status Update PPT | P
[5 empty] | 10:30 | 12:30 | 15 | PE review of Project Plan
| 10:45 | 12:45 | 30 | PE review of Initial Status Update PPT | 10:45 | 12:45 | 45 | Follow team created Class 8 Agenda | P
| 11:15 | 13:15 | 15 | PE review of Project Plan |  |  |  |  | T | P | 90
[10 empty] | T | 15
| 11:30 | 13:30 | 15 | Follow team created Class 8 Agenda & continue Project Technical Work |  |  |  |  | P | A | 5
| 11:45 | 13:45 | 5 | Wrap Up |  |  |  |  | A
|  | Total Duration (min) | 110 |  |  |  | 110
Teams will be assigned to a track
You will be notified which track to follow
Snapshot from S21 (no changes after early Feb)
| 8 |  | Webex Teams - Project space (by team)
Webex Teams - PE space (multiple teams w/ common PE)
Webex Meetings
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| Track A |  |  |  | Track B
| 10:10 | 12:20 | 30 | Follow team created Class 8 Agenda | 10:10 | 12:20 | 30 | PE review of Initial Status Update PPT
| 10:40 | 12:50 | 30 | PE review of Initial Status Update PPT | 10:40 | 12:50 | 30 | Follow team created Class 8 Agenda
| 11:10 | 1:20 | 50 | Follow team created Class 8 Agenda & continue Project Technical Work
|  | Total Duration (min) | 110 |  |  |  | 110
Teams will be assigned to a track
You will be notified which track to follow

## old DAY 9
F22
| 9 |  |  | Full class activity |  |  | SCAFFOLDING NO LONGER NEEDED F23 and onward
Team activity
category
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 5 | Preliminary Design Review Q&A | [8 empty] | A
[14 empty] | P | 95
| Track A |  |  |  | Track B |  |  |  | Track C |  |  |  |  | T | 0
| 10:05 | 12:05 | 95 | Draft BDR Poster | 10:05 | 10:05 | 45 | Client Meeting #1 | 10:05 | 12:05 | 50 | Project Work | P | A | 15
[5 empty] | 10:50 | 10:50 | 50 | Project Work | 10:55 | 12:55 | 45 | Client Meeting #1 | P
| 11:40 | 13:40 | 10 | Wrap Up | [8 empty] | A
|  | Total Duration (min) | 110 |  |  |  | #REF! |  |  |  | #REF!
Post-Class Ticket Out (complete outside of class)
Teams will be assigned to a track
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor
| 3 |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
Webex Meetings
MC
PE/CE |  |  |  | start in PE Team Space | [8 empty] | category
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 5 | Week 2 Schedule Intro | [8 empty] | A
| 10:05 | 12:05 | 10 | ENGINEERING DESIGN PROCESS Q&A | [8 empty] | T
|  |  | shift to Webex meeting |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space
| Track A |  |  |  | Track B |  |  |  | Track B |  |  |  |  | P | 45
| 10:15 | 12:15 | 45 | Sponsor Kickoff | 10:15 | 12:15 | 30 | Meet with Chief Engineer | 10:15 | 12:15 | 30 | Meet with Chief Engineer | T | T | 55
| 11:00 | 13:00 | 45 | Initial Customer Needs & Reqs | 10:45 | 12:45 | 45 | Initial Customer Needs & Reqs | 10:45 | 12:45 | 45 | Initial Customer Needs & Reqs | P | A | 10
[5 empty] | 11:30 | 13:30 | 15 | Group review of Needs & Reqs | 11:30 | 13:30 | 15 | Group review of Needs & Reqs
shift to PE Team space
| 11:45 | 13:45 | 5 | Wrap Up | [8 empty] | A
|  | Total Duration (min) | 110 |  |  |  | 110 |  |  |  | 105 |  | A
Post-Class Ticket Out (complete outside of class)
Teams will be assigned to a track
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor
Snapshot from S21 (no changes after early Feb)
| 3 |  | Webex Teams - Project space (by team)
Webex Teams - PE space (multiple teams w/ common PE)
Webex Meetings
start in PE Team Space
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| 10:10 | 12:20 | 5 | Week 2 Schedule Intro
| 10:15 | 12:25 | 15 | Review of ENGINEERING DESIGN PROCESS
|  |  | shift to Webex meeting |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space
| Track A |  |  |  | Track B |  |  |  | Track B
| 10:30 | 12:40 | 45 | Sponsor Kickoff | 10:30 | 12:40 | 30 | CE meeting with team | 10:30 | 12:40 | 30 | CE meeting with team
| 11:15 | 1:25 | 45 | Initial Customer Needs & Reqs | 11:00 | 1:10 | 45 | Initial Customer Needs & Reqs | 11:00 | 1:10 | 45 | Initial Customer Needs & Reqs
[5 empty] | 11:45 | 1:55 | 15 | Group review of Needs & Reqs | 11:45 | 1:55 | 15 | Group review of Needs & Reqs
|  | Total Duration (min) | 110 |  |  |  | 110 |  |  |  | 110
Post-class Ticket Out (complete outside of class)
Teams will be assigned to a track
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor

## old DAY 10
F22
| 10 |  |  | Full class activity |  |  | SCAFFOLDING NO LONGER NEEDED F23 and onward
Team activity
category
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
[14 empty] | P | 100
| Track A |  |  |  | Track B |  |  |  | Track C |  |  |  |  | T | 0
| 10:00 | 12:00 | 100 | Draft BDR Poster | 10:00 | 12:00 | 45 | Client Meeting #1 | 10:00 | 12:00 | 55 | Project Work | P | A | 10
[5 empty] | 10:45 | 12:45 | 55 | Project Work | 10:55 | 12:55 | 45 | Client Meeting #1 | P
| 11:40 | 13:40 | 10 | Wrap Up | [8 empty] | A
|  | Total Duration (min) | 110 |  |  |  | #REF! |  |  |  | #REF!
Post-Class Ticket Out (complete outside of class)
Teams will be assigned to a track
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor
| 3 |  | Webex Teams - Project Space (by team)
Webex Teams - PE Space (multiple teams w/ common PE)
Webex Meetings
MC
PE/CE |  |  |  | start in PE Team Space | [8 empty] | category
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| 10:00 | 12:00 | 5 | Week 2 Schedule Intro | [8 empty] | A
| 10:05 | 12:05 | 10 | ENGINEERING DESIGN PROCESS Q&A | [8 empty] | T
|  |  | shift to Webex meeting |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space
| Track A |  |  |  | Track B |  |  |  | Track B |  |  |  |  | P | 45
| 10:15 | 12:15 | 45 | Sponsor Kickoff | 10:15 | 12:15 | 30 | Meet with Chief Engineer | 10:15 | 12:15 | 30 | Meet with Chief Engineer | T | T | 55
| 11:00 | 13:00 | 45 | Initial Customer Needs & Reqs | 10:45 | 12:45 | 45 | Initial Customer Needs & Reqs | 10:45 | 12:45 | 45 | Initial Customer Needs & Reqs | P | A | 10
[5 empty] | 11:30 | 13:30 | 15 | Group review of Needs & Reqs | 11:30 | 13:30 | 15 | Group review of Needs & Reqs
shift to PE Team space
| 11:45 | 13:45 | 5 | Wrap Up | [8 empty] | A
|  | Total Duration (min) | 110 |  |  |  | 110 |  |  |  | 105 |  | A
Post-Class Ticket Out (complete outside of class)
Teams will be assigned to a track
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor
Snapshot from S21 (no changes after early Feb)
| 3 |  | Webex Teams - Project space (by team)
Webex Teams - PE space (multiple teams w/ common PE)
Webex Meetings
start in PE Team Space
| Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity | Start time |  | Duration (min) | Activity
| 10:10 | 12:20 | 5 | Week 2 Schedule Intro
| 10:15 | 12:25 | 15 | Review of ENGINEERING DESIGN PROCESS
|  |  | shift to Webex meeting |  |  |  | shift to Project Team Space |  |  |  | shift to Project Team Space
| Track A |  |  |  | Track B |  |  |  | Track B
| 10:30 | 12:40 | 45 | Sponsor Kickoff | 10:30 | 12:40 | 30 | CE meeting with team | 10:30 | 12:40 | 30 | CE meeting with team
| 11:15 | 1:25 | 45 | Initial Customer Needs & Reqs | 11:00 | 1:10 | 45 | Initial Customer Needs & Reqs | 11:00 | 1:10 | 45 | Initial Customer Needs & Reqs
[5 empty] | 11:45 | 1:55 | 15 | Group review of Needs & Reqs | 11:45 | 1:55 | 15 | Group review of Needs & Reqs
|  | Total Duration (min) | 110 |  |  |  | 110 |  |  |  | 110
Post-class Ticket Out (complete outside of class)
Teams will be assigned to a track
You will be notified which track to follow
You will receive email invitation to Webex Meetings with Sponsor

## Summary
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | total | %
Project technical work | (P) | 15 | 80 | 45 | 70 | 60 | 95 | 80 | 90 | 90 | 90 | 625 | 63.13%
Team development / Design process refresher | (T) | 35 | 0 | 55 | 30 | 0 | 10 | 10 | 15 | 15 | 15 | 170 | 17.17%
Administrative tasks | (A) | 40 | 30 | 10 | 10 | 50 | 5 | 10 | 5 | 5 | 5 | 165 | 16.67%
above numbers ALL pulled from prior sheets and autoupdated
Total class time is 110/day