## Sheet1
| Project Initiation |  |  |  |  | Project Planning |  |  |  | Preliminary Design |  |  | Project Execution -> Final Design
Week | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15
On-Site Meeting # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Onboarding Sessions
Project Scoping Sessions
Client Meeting #1 - Kickoff
Benchmarking Memo
Individual CE Feedback
Needs & Requirements Spreadsheet
Concept Generation & Selection
Client Meeting #2, #3, #4
Technical Progress & Project Mgmt
Board of Directors Review
Peer Evaluation
System Design Report
Detail Individual Design Report
Design Showcase
Final Design Review
Final Design Report & Poster
System Evaluation
All dates are approximate. Consult syllabus and Task and Due Dates page in Wiki for exact due dates
yellow |  | Graded Assignment
green |  | Student / CE Meeting
orange |  | Team / Client Meeting
blue |  | Guided On-Site Meeting Sessions
grey |  | ICF Factor